## Sheet1
ID | Task Name | Resource Names
0 | Commercial Office Space Construction
1 | General Conditions
2 | Receiving notice to proceed and sign contract | General Manager
3 | Submitting bond and insurance documents | Project Management,General Manager[25%]
4 | Preparing and submitting project schedule | Project Management[25%],Scheduler
5 | Preparing and submitting schedule of values | General Manager[10%],Project Management
6 | Obtaining building permits | Project Management[50%],Procurement[50%]
7 | Building permits obtained
8 | Submitting preliminary shop drawings | Project Management[50%],Procurement[50%],Flight Fare[$300.00]
9 | Submitting monthly requests for payment
10 | Long Lead Procurement
11 | Submitting shop drawings and order long lead items - steel | Steel Erection Contractor Management
12 | Submitting shop drawings and order long lead items - roofing | Roofing Contractor Management
13 | Submitting shop drawings and order long lead items - elevator | Elevator Contractor Management
14 | Submitting shop drawings and order long lead items - plumbing | Plumbing Contractor Management
15 | Submitting shop drawings and order long lead items - electric | Electric Contractor Management
16 | Submitting shop drawings and order long lead items - HVAC | HVAC Contractor Management
17 | Detail, fabricate and deliver steel | Steel Erection Contractor Management[50%],Steel Erection Contractor[50%]
18 | Procurement completed
19 | Mobilize on Site
20 | Install temporary power | Electric Contractor
21 | Install temporary water service | Plumbing Contractor
22 | Set up site office | Superintendent,Labor Unit[10%]
23 | Set line and grade benchmarks | Survey Unit
24 | Prepare site - lay down yard and temporary fencing | Site Grading Contractor,Labor Unit[10%]
25 | Mobilization completed
26 | Site Grading and Utilities
27 | Clear and grub site | Site Grading Contractor
28 | Stone site access and temporary parking area | Site Grading Contractor
29 | Rough grade site (cut and fill) | Site Grading Contractor
30 | Install storm drainage | Site Grading Contractor
31 | Install exterior fire line and building fire riser | Plumbing Contractor
32 | Perform final site grading | Site Grading Contractor
33 | Erect building batter boards and layout building | Survey Unit
34 | Excavation and Foundations
35 | Excavate foundations | Site Grading Contractor[50%],Steel[5 ton]
36 | Excavate elevator pit | Site Grading Contractor
37 | Form column piers and spread foundations
38 | Rough-in electric and plumbing in elevator | Plumbing Contractor,Electric Contractor
39 | Form elevator pit walls | Rough Carpenter Unit
40 | Set reinforcing and anchor bolts | Rough Carpenter Unit
41 | Pour column piers and foundations | Concrete Unit
42 | Pour concrete elevator walls | Concrete Unit
43 | Cure elevator wall concrete | Labor Unit[10%]
44 | Cure piers and foundations | Labor Unit[10%]
45 | Strip wall forms | Labor Unit[10%]
46 | Strip column piers and foundation forms | Labor Unit
47 | Install pneumatic tube in elevator pit | Elevator Contractor
48 | Prepare and pour concrete floor in elevator pit | Concrete Unit
49 | Column Erection and Miscellaneous steel works
50 | Erect steel columns, beams and joint - 1st and 2nd floors | Steel Erection Contractor
51 | Erect steel columns, beams and joint - 3rd floor and roof | Steel Erection Contractor
52 | Install miscellaneous iron and bracing - 1st and 2nd floors | Steel Erection Contractor[75%]
53 | Install miscellaneous iron and bracing - 3rd floor and roof | Steel Erection Contractor[75%]
54 | Install stairs and miscellaneous iron railing | Steel Erection Contractor[50%]
55 | Touch-up paint on steel | Steel Erection Contractor[20%]
56 | Forming, Pouring, & Curing - Floors and Roof
57 | Form 2nd floor including all floor openings | Rough Carpenter Unit,Labor Unit[20%]
58 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Labor Unit[33%],Plumbing Contractor[33%],Electric Contractor[33%]
59 | Pour 2nd floor slab | Concrete Unit
60 | Cure 2nd floor slab | Labor Unit[10%]
61 | Strip forms from 2nd floor slab | Labor Unit
62 | Form 3rd floor including all floor openings | Rough Carpenter Unit[50%],Labor Unit[20%]
63 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Labor Unit[33%],Plumbing Contractor[33%],Electric Contractor[33%]
64 | Pour 3rd floor slab | Concrete Unit
65 | Cure 3rd floor slab | Labor Unit[10%]
66 | Strip forms from 3rd floor slab | Labor Unit
67 | Form roof slab including all floor openings | Rough Carpenter Unit,Labor Unit[20%]
68 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Labor Unit[33%],Plumbing Contractor[33%],Electric Contractor[33%]
69 | Pour roof slab | Concrete Unit
70 | Cure roof slab | Labor Unit[10%]
71 | Strip forms from roof slab | Labor Unit
72 | Form 1st floor | Rough Carpenter Unit
73 | Install electrical underground | Electric Contractor
74 | Install plumbing underground | Plumbing Contractor
75 | Install rebar and in-floor utilities | Labor Unit[33%],Plumbing Contractor[33%],Electric Contractor[33%]
76 | Pour 1st floor slab | Concrete Unit
77 | Cure 1st floor slab | Labor Unit[10%]
78 | Strip forms from 1st floor slab | Labor Unit
79 | Carpentry Work
80 | Install exterior sheathing and metal studs | Drywall Contractor
81 | Masonry Work
82 | Rough-in plumbing at toilets and masonry walls | Plumbing Contractor
83 | Lay masonry at core, mechanical, and toilets | Masonry Contractor
84 | Install exterior masonry work | Masonry Contractor
85 | Install roof drains | Roofing Contractor
86 | Install tile in toilet rooms | Tile Contractor
87 | Clean masonry | Masonry Contractor[50%]
88 | Clean toilet room tile | Tile Contractor[50%]
89 | Roofing
90 | Install flashing at parapet walls | Roofing Contractor
91 | Pour lightweight concrete roof fill | Roofing Contractor
92 | Install seamless roofing material | Roofing Contractor
93 | Spread stone ballast on seamless roof | Roofing Contractor
94 | Set rooftop equipment | HVAC Contractor
95 | Window wall and store front closures
96 | Install window wall aluminum and glass | Window Contractor
97 | Install interior stud walls and drywall | Drywall Contractor
98 | Install interior doors and hardware | Finish Carpenter Unit
99 | Install store front doors and hardware | Window Contractor
100 | Finishing Building Works
101 | Install millwork and wood trim | Finish Carpenter Unit
102 | Paint walls and woodwork | Painting Contractor
103 | Install conduit at ceiling plenum space | Electric Contractor
104 | Install duct in ceiling plenum space | HVAC Contractor
105 | Install ceiling grid | Drywall Contractor
106 | Install ceiling tile | Drywall Contractor
107 | Hang wallpaper | Painting Contractor
108 | Install building carpet | Carpet Contractor
109 | Install hardware and accessories | Finish Carpenter Unit
110 | Complete interior and exterior sod and plantings | Landscape Contractor
111 | Pave, curb, and stripe parking lot | Paving Contractor
112 | Building works finished
113 | Setting and Testing Elevators
114 | Set elevator equipment in shafts | Elevator Contractor
115 | Set equipment in mechanical room | Elevator Contractor
116 | Test and align doors and equipment | Elevator Contractor
117 | Plumbing
118 | Rough-in plumbing in drywall walls | Plumbing Contractor
119 | Tie-in fire line riser and set valves | Plumbing Contractor
120 | Set plumbing fixtures and trim | Plumbing Contractor
121 | Flush, test, and clean piping and fixtures | Plumbing Contractor
122 | Plumbing works completed
123 | Electrical Works
124 | Rough-in electrical in masonry walls | Electric Contractor
125 | Rough-in electrical in drywall walls | Electric Contractor
126 | Pull wire in conduit and set area transformers | Electric Contractor
127 | Install and terminate electrical devices | Electric Contractor
128 | Make electrical terminations for HVAC equipment | Electric Contractor
129 | Install light fixtures - test and clean | Electric Contractor
130 | Electrical works completed
131 | Heating and Ventilating - AC
132 | Set equipment in mechanical room | HVAC Contractor
133 | Rough-in mechanical in masonry walls | HVAC Contractor
134 | Rough-in mechanical in drywall walls | HVAC Contractor
135 | Install duct in building chase | HVAC Contractor
136 | Set HVAC trim and test and balance system | HVAC Contractor
137 | Final Clean-up and Occupancy
138 | Install hard tile flooring in common areas | Tile Contractor
139 | Clean hard tile floors | Tile Contractor[50%]
140 | Remove debris from building and do final clean-up | Labor Unit
141 | Substantial completion date | Superintendent
142 | Ready for Occupancy
143 | Complete Final Inspections
144 | Complete elevator inspection and certification | Elevator Contractor
145 | Perform architect's inspection | Superintendent[50%],Project Management[50%]
146 | Perform local building agency inspection | Project Management[50%],Superintendent[50%]
147 | Perform Fire Marshal's inspection | Superintendent[50%],Project Management[50%]
148 | Final inspection completed
149 | Project Closure
150 | Complete punch list items from all inspections | Superintendent[11%],Labor Unit[11%],Plumbing Contractor[11%],Electric Contractor[11%],HVAC Contractor[11%],Drywall Contractor[11%],Carpet Contractor[11%],Paving Contractor[11%],Painting Contractor[11%]
151 | Obtain certificate of occupancy | Project Management
152 | Issue final completion documents including warranties | Project Management
153 | Issue final request for payment | Project Management[33%],Accounting[33%],General Manager[33%]
154 | Payments cleared & Project completed successfully

## Sheet2
Resource Name | Type | Material Label | Initials | Group | Max. Units | Std. Rate | Ovt. Rate | Cost/Use | Accrue At | Base Calendar | Code | Cost | Work
General Manager | Work |  | GM |  | 100% | $100.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 0 hrs
Steel | Material | ton | Steel |  |  | 600 |  | 50 | Prorated |  |  | 3050 | 5 ton
Flight Fare | Cost |  | Flight Fare | [5 empty] | Start |  |  | 300
Steel Erection Contractor Management | Work |  | Steel Erection Contractor Mgmt |  | 100% | $25.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 80 hrs
Site Grading Contractor | Work |  | Site Grading Contractor |  | 100% | $12.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 672 | 56 hrs
Steel Erection Contractor | Work |  | Steel Erection Contractor |  | 100% | $12.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 0 hrs
Project Management | Work |  | PM |  | 100% | $90.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 3960 | 44 hrs
Procurement | Work |  | Procurement |  | 100% | $35.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 1400 | 40 hrs
Scheduler | Work |  | Scheduler |  | 100% | $25.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 0 hrs
Accounting | Work |  | Accounting |  | 100% | $30.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 0 hrs
Superintendent | Work |  | Superintendent |  | 100% | $40.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 4 hrs
Survey Unit | Work |  | Survey |  | 100% | $12.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 0 hrs
Rough Carpenter Unit | Work |  | Rouch Carpenter |  | 100% | $12.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 20 hrs
Labor Unit | Work |  | Labor |  | 100% | $12.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 13.6 hrs
Concrete Unit | Work |  | Concrete Unit |  | 100% | $12.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 0 hrs
Finish Carpenter Unit | Work |  | Finish Carpenter |  | 100% | $12.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 0 hrs
Plumbing Contractor | Work |  | Plumbing Contractor |  | 100% | $12.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 32 hrs
Plumbing Contractor Management | Work |  | Plumbing Contractor Mgmt |  | 100% | $25.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 0 hrs
Electric Contractor | Work |  | Electic Contractor |  | 100% | $12.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 32 hrs
Electric Contractor Management | Work |  | Electic Contractor Mgmt |  | 100% | $25.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 0 hrs
HVAC Contractor | Work |  | HVAC Contractor |  | 100% | $12.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 0 hrs
HVAC Contractor Management | Work |  | HVAC Contractor Mgmt |  | 100% | $25.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 0 hrs
Elevator Contractor | Work |  | Elevator Contractor |  | 100% | $12.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 0 hrs
Elevator Contractor Management | Work |  | Elevator Contractor Mgmt |  | 100% | $25.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 0 hrs
Drywall Contractor | Work |  | Drywall Contractor |  | 100% | $12.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 0 hrs
Masonry Contractor | Work |  | Masonry Contractor |  | 100% | $12.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 0 hrs
Tile Contractor | Work |  | Tile Contractor |  | 100% | $12.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 0 hrs
Roofing Contractor | Work |  | Roofing Contractor |  | 100% | $12.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 0 hrs
Roofing Contractor Management | Work |  | Roofing Contractor Mgmt |  | 100% | $25.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 0 hrs
Window Contractor | Work |  | Window Contractor |  | 100% | $12.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 0 hrs
Carpet Contractor | Work |  | Carpet Contractor |  | 100% | $12.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 0 hrs
Landscape Contractor | Work |  | Landscape Contractor |  | 100% | $12.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 0 hrs
Paving Contractor | Work |  | Paving Contractor |  | 100% | $12.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 0 hrs
Painting Contractor | Work |  | Painting Contractor |  | 100% | $12.00/hr | $0.00/hr | 0 | Prorated | Construction Calendar |  | 0 | 0 hrs