## Task_Table1
Name | Assignee | Duration | Start Date | Finish Date
Commercial Office Space Construction |  | 349 days? | 2019 October 21 8:30 AM | 2021 February 23 12:30 PM
General Conditions |  | 24 days | 2019 October 21 8:30 AM | 2019 November 21 5:30 PM
Receiving notice to proceed and sign contract | General Manager | 3 days | 2019 October 21 8:30 AM | 2019 October 23 5:30 PM
Submitting bond and insurance documents | Project Management,General Manager[25%] | 2 days | 2019 October 24 8:30 AM | 2019 October 25 5:30 PM
Preparing and submitting project schedule | Project Management[25%],Scheduler | 2 days | 2019 October 28 8:30 AM | 2019 October 29 5:30 PM
Preparing and submitting schedule of values | General Manager[10%],Project Management | 2 days | 2019 October 30 8:30 AM | 2019 October 31 5:30 PM
Obtaining building permits | Project Management[50%],Procurement[50%] | 4 days | 2019 November 05 8:30 AM | 2019 November 08 5:30 PM
Building permits obtained |  | 0 days | 2019 November 08 5:30 PM | 2019 November 08 5:30 PM
Submitting preliminary shop drawings | Project Management[50%],Procurement[50%],Flight Fare[$300.00] | 2 wks | 2019 November 08 8:30 AM | 2019 November 21 5:30 PM
Submitting monthly requests for payment |  | 1 day | 2019 October 24 8:30 AM | 2019 October 24 5:30 PM
Long Lead Procurement |  | 70 days | 2019 October 25 8:30 AM | 2020 January 30 5:30 PM
Submitting shop drawings and order long lead items - steel | Steel Erection Contractor Management | 2 wks | 2019 October 25 8:30 AM | 2019 November 07 5:30 PM
Submitting shop drawings and order long lead items - roofing | Roofing Contractor Management | 1.2 wks | 2019 November 22 8:30 AM | 2019 November 29 5:30 PM
Submitting shop drawings and order long lead items - elevator | Elevator Contractor Management | 2 wks | 2019 November 22 8:30 AM | 2019 December 05 5:30 PM
Submitting shop drawings and order long lead items - plumbing | Plumbing Contractor Management | 2 wks | 2019 November 22 8:30 AM | 2019 December 05 5:30 PM
Submitting shop drawings and order long lead items - electric | Electric Contractor Management | 2 wks | 2019 November 22 8:30 AM | 2019 December 05 5:30 PM
Submitting shop drawings and order long lead items - HVAC | HVAC Contractor Management | 2 wks | 2019 November 22 8:30 AM | 2019 December 06 5:30 PM
HVAC - Shop Drawing Approval | HVAC Contractor Management | 1 day | 2019 December 03 8:00 AM | 2019 December 03 5:00 PM
Detail, fabricate and deliver steel | Steel Erection Contractor Management[50%],Steel Erection Contractor[50%] | 12 wks | 2019 November 08 8:30 AM | 2020 January 30 5:30 PM
Procurement completed |  | 0 days | 2020 January 30 5:30 PM | 2020 January 30 5:30 PM
Mobilize on Site |  | 11 days? | 2019 October 24 8:30 AM | 2019 November 07 5:30 PM
Install temporary power | Electric Contractor | 2 days | 2019 October 24 8:30 AM | 2019 October 25 5:30 PM
Install temporary water service | Plumbing Contractor | 2 days | 2019 October 24 8:30 AM | 2019 October 25 5:30 PM
Set up site office | Superintendent,Labor Unit[10%] | 3 days | 2019 October 28 8:30 AM | 2019 October 30 5:30 PM
Set line and grade benchmarks | Survey Unit | 3 days | 2019 October 31 8:30 AM | 2019 November 04 5:30 PM
Prepare site - lay down yard and temporary fencing | Site Grading Contractor,Labor Unit[10%] | 2 days | 2019 November 05 8:30 AM | 2019 November 06 5:30 PM
Mobilization completed |  | 1 day? | 2019 November 07 8:30 AM | 2019 November 07 5:30 PM
Site Grading and Utilities |  | 35 days | 2019 November 07 8:30 AM | 2019 December 25 5:30 PM
Clear and grub site | Site Grading Contractor | 3 days | 2019 November 07 8:30 AM | 2019 November 11 5:30 PM
Stone site access and temporary parking area | Site Grading Contractor | 2 days | 2019 November 12 8:30 AM | 2019 November 13 5:30 PM
Rough grade site (cut and fill) | Site Grading Contractor | 1 wk | 2019 November 14 8:30 AM | 2019 November 20 5:30 PM
Install storm drainage | Site Grading Contractor | 2 wks | 2019 November 21 8:30 AM | 2019 December 04 5:30 PM
Install exterior fire line and building fire riser | Plumbing Contractor | 2 wks | 2019 November 21 8:30 AM | 2019 December 04 5:30 PM
Perform final site grading | Site Grading Contractor | 2 wks | 2019 December 05 8:30 AM | 2019 December 18 5:30 PM
Erect building batter boards and layout building | Survey Unit | 1 wk | 2019 December 19 8:30 AM | 2019 December 25 5:30 PM
Excavation and Foundations |  | 34 days | 2019 December 26 8:30 AM | 2020 February 11 5:30 PM
Excavate foundations | Site Grading Contractor[50%],Steel[5 ton] | 2 wks | 2019 December 26 8:30 AM | 2020 January 08 5:30 PM
Excavate elevator pit | Site Grading Contractor | 2 days | 2020 January 09 8:30 AM | 2020 January 10 5:30 PM
Form column piers and spread foundations |  | 4 days | 2020 January 09 8:30 AM | 2020 January 14 5:30 PM
Rough-in electric and plumbing in elevator | Plumbing Contractor,Electric Contractor | 4 days | 2020 January 13 8:30 AM | 2020 January 16 5:30 PM
Form elevator pit walls | Rough Carpenter Unit | 4 days | 2020 January 17 8:30 AM | 2020 January 22 5:30 PM
Set reinforcing and anchor bolts | Rough Carpenter Unit | 4 days | 2020 January 15 8:30 AM | 2020 January 20 5:30 PM
Pour column piers and foundations | Concrete Unit | 5 days | 2020 January 21 8:30 AM | 2020 January 27 5:30 PM
Pour concrete elevator walls | Concrete Unit | 1 day | 2020 January 23 8:30 AM | 2020 January 23 5:30 PM
Cure elevator wall concrete | Labor Unit[10%] | 7 days | 2020 January 24 8:30 AM | 2020 February 03 5:30 PM
Cure piers and foundations | Labor Unit[10%] | 7 days | 2020 January 28 8:30 AM | 2020 February 05 5:30 PM
Strip wall forms | Labor Unit[10%] | 1 day | 2020 February 04 8:30 AM | 2020 February 04 5:30 PM
Strip column piers and foundation forms | Labor Unit | 3 days | 2020 February 06 8:30 AM | 2020 February 10 5:30 PM
Install pneumatic tube in elevator pit | Elevator Contractor | 3 days | 2020 February 05 8:30 AM | 2020 February 07 5:30 PM
Prepare and pour concrete floor in elevator pit | Concrete Unit | 1 day | 2020 February 11 8:30 AM | 2020 February 11 5:30 PM
Column Erection and Miscellaneous steel works |  | 50 days | 2020 February 11 8:30 AM | 2020 April 20 5:30 PM
Erect steel columns, beams and joint - 1st and 2nd floors | Steel Erection Contractor | 3 wks | 2020 February 11 8:30 AM | 2020 March 02 5:30 PM
Erect steel columns, beams and joint - 3rd floor and roof | Steel Erection Contractor 2 | 2 wks | 2020 March 03 8:30 AM | 2020 March 16 5:30 PM
Install miscellaneous iron and bracing - 1st and 2nd floors | Steel Erection Contractor[75%] | 2 wks | 2020 March 03 8:30 AM | 2020 March 16 5:30 PM
Install miscellaneous iron and bracing - 3rd floor and roof | Steel Erection Contractor 2[75%] | 2 wks | 2020 March 17 8:30 AM | 2020 March 30 5:30 PM
Install stairs and miscellaneous iron railing | Steel Erection Contractor[50%] | 2 wks | 2020 March 31 8:30 AM | 2020 April 13 5:30 PM
Touch-up paint on steel | Steel Erection Contractor[20%] | 1 wk | 2020 April 14 8:30 AM | 2020 April 20 5:30 PM
Forming, Pouring, & Curing - Floors and Roof |  | 85 days | 2020 March 03 8:30 AM | 2020 June 29 5:30 PM
Form 2nd floor including all floor openings | Rough Carpenter Unit,Labor Unit[20%] | 5 days | 2020 April 21 8:30 AM | 2020 April 27 5:30 PM
Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Labor Unit[33%],Plumbing Contractor[33%],Electric Contractor[33%] | 5 days | 2020 March 03 8:30 AM | 2020 March 09 5:30 PM
Pour 2nd floor slab | Concrete Unit | 4 days | 2020 April 28 8:30 AM | 2020 May 01 5:30 PM
Cure 2nd floor slab | Labor Unit[10%] | 7 days | 2020 May 04 8:30 AM | 2020 May 12 5:30 PM
Strip forms from 2nd floor slab | Labor Unit | 2 days | 2020 May 13 8:30 AM | 2020 May 14 5:30 PM
Form 3rd floor including all floor openings | Rough Carpenter Unit[50%],Labor Unit[20%] | 5 days | 2020 May 13 8:30 AM | 2020 May 19 5:30 PM
Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Labor Unit[33%],Plumbing Contractor[33%],Electric Contractor[33%] | 5 days | 2020 May 13 8:30 AM | 2020 May 19 5:30 PM
Pour 3rd floor slab | Concrete Unit | 4 days | 2020 May 20 8:30 AM | 2020 May 25 5:30 PM
Cure 3rd floor slab | Labor Unit[10%] | 7 days | 2020 May 26 8:30 AM | 2020 June 03 5:30 PM
Strip forms from 3rd floor slab | Labor Unit | 2 days | 2020 June 04 8:30 AM | 2020 June 05 5:30 PM
Form roof slab including all floor openings | Rough Carpenter Unit,Labor Unit[20%] | 5 days | 2020 June 04 8:30 AM | 2020 June 10 5:30 PM
Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Labor Unit[33%],Plumbing Contractor[33%],Electric Contractor[33%] | 5 days | 2020 June 04 8:30 AM | 2020 June 10 5:30 PM
Pour roof slab | Concrete Unit | 4 days | 2020 June 11 8:30 AM | 2020 June 16 5:30 PM
Cure roof slab | Labor Unit[10%] | 7 days | 2020 June 17 8:30 AM | 2020 June 25 5:30 PM
Strip forms from roof slab | Labor Unit | 2 days | 2020 June 26 8:30 AM | 2020 June 29 5:30 PM
Form 1st floor | Rough Carpenter Unit | 4 days | 2020 May 15 8:30 AM | 2020 May 20 5:30 PM
Install electrical underground | Electric Contractor | 1 wk | 2020 May 15 8:30 AM | 2020 May 21 5:30 PM
Install plumbing underground | Plumbing Contractor | 1 wk | 2020 May 15 8:30 AM | 2020 May 21 5:30 PM
Install rebar and in-floor utilities | Labor Unit[33%],Plumbing Contractor[33%],Electric Contractor[33%] | 4 days | 2020 May 15 8:30 AM | 2020 May 20 5:30 PM
Pour 1st floor slab | Concrete Unit | 4 days | 2020 May 22 8:30 AM | 2020 May 27 5:30 PM
Cure 1st floor slab | Labor Unit[10%] | 7 days | 2020 May 28 8:30 AM | 2020 June 05 5:30 PM
Strip forms from 1st floor slab | Labor Unit | 2 days | 2020 June 08 8:30 AM | 2020 June 09 5:30 PM
Carpentry Work |  | 15 days | 2020 June 30 8:30 AM | 2020 July 20 5:30 PM
Install exterior sheathing and metal studs | Drywall Contractor | 3 wks | 2020 June 30 8:30 AM | 2020 July 20 5:30 PM
Masonry Work |  | 110 days | 2020 March 31 8:30 AM | 2020 September 01 12:30 PM
Rough-in plumbing at toilets and masonry walls | Plumbing Contractor | 4 wks | 2020 June 10 8:30 AM | 2020 July 07 5:30 PM
Lay masonry at core, mechanical, and toilets | Masonry Contractor | 4 wks | 2020 March 31 8:30 AM | 2020 April 27 5:30 PM
Install exterior masonry work | Masonry Contractor | 5 wks | 2020 July 21 8:30 AM | 2020 August 25 12:30 PM
Install roof drains | Roofing Contractor | 2 days | 2020 August 25 1:30 PM | 2020 August 27 12:30 PM
Install tile in toilet rooms | Tile Contractor | 2 wks | 2020 July 08 8:30 AM | 2020 July 21 5:30 PM
Clean masonry | Masonry Contractor[50%] | 1 wk | 2020 August 25 1:30 PM | 2020 September 01 12:30 PM
Clean toilet room tile | Tile Contractor[50%] | 1 wk | 2020 July 22 8:30 AM | 2020 July 28 5:30 PM
Roofing |  | 31 days | 2020 August 27 1:30 PM | 2020 October 12 12:30 PM
Install flashing at parapet walls | Roofing Contractor | 4 days | 2020 August 27 1:30 PM | 2020 September 02 12:30 PM
Pour lightweight concrete roof fill | Roofing Contractor | 2 days | 2020 September 02 1:30 PM | 2020 September 04 12:30 PM
Install seamless roofing material | Roofing Contractor | 5 days | 2020 September 11 1:30 PM | 2020 September 18 12:30 PM
Spread stone ballast on seamless roof | Roofing Contractor | 5 days | 2020 September 18 1:30 PM | 2020 September 25 12:30 PM
Set rooftop equipment | HVAC Contractor | 2 wks | 2020 September 25 1:30 PM | 2020 October 12 12:30 PM
Window wall and store front closures |  | 60 days | 2020 August 25 1:30 PM | 2020 November 18 12:30 PM
Install window wall aluminum and glass | Window Contractor | 5 wks | 2020 August 25 1:30 PM | 2020 September 29 12:30 PM
Install interior stud walls and drywall | Drywall Contractor | 5 wks | 2020 September 29 1:30 PM | 2020 November 04 12:30 PM
Install interior doors and hardware | Finish Carpenter Unit | 2 wks | 2020 November 04 1:30 PM | 2020 November 18 12:30 PM
Install store front doors and hardware | Window Contractor | 3 wks | 2020 August 25 1:30 PM | 2020 September 15 12:30 PM
Finishing Building Works |  | 80 days | 2020 September 29 1:30 PM | 2021 January 21 12:30 PM
Install millwork and wood trim | Finish Carpenter Unit | 3 wks | 2020 November 04 1:30 PM | 2020 November 25 12:30 PM
Paint walls and woodwork | Painting Contractor | 4 wks | 2020 November 25 1:30 PM | 2020 December 23 12:30 PM
Install conduit at ceiling plenum space | Electric Contractor | 3 wks | 2020 September 29 1:30 PM | 2020 October 21 12:30 PM
Install duct in ceiling plenum space | HVAC Contractor | 3 wks | 2020 November 04 1:30 PM | 2020 November 25 12:30 PM
Install ceiling grid | Drywall Contractor | 2 wks | 2020 November 25 1:30 PM | 2020 December 09 12:30 PM
Install ceiling tile | Drywall Contractor | 2 wks | 2020 December 09 1:30 PM | 2020 December 23 12:30 PM
Hang wallpaper | Painting Contractor | 2 wks | 2020 December 23 1:30 PM | 2021 January 07 12:30 PM
Install building carpet | Carpet Contractor | 4 wks | 2020 December 23 1:30 PM | 2021 January 21 12:30 PM
Install hardware and accessories | Finish Carpenter Unit | 3 wks | 2020 December 23 1:30 PM | 2021 January 14 12:30 PM
Complete interior and exterior sod and plantings | Landscape Contractor | 2 wks | 2020 December 23 1:30 PM | 2021 January 07 12:30 PM
Pave, curb, and stripe parking lot | Paving Contractor | 2 wks | 2021 January 07 1:30 PM | 2021 January 21 12:30 PM
Building works finished |  | 0 days | 2021 January 21 12:30 PM | 2021 January 21 12:30 PM
Setting and Testing Elevators |  | 40 days | 2020 April 28 8:30 AM | 2020 June 22 5:30 PM
Set elevator equipment in shafts | Elevator Contractor | 4 wks | 2020 April 28 8:30 AM | 2020 May 25 5:30 PM
Set equipment in mechanical room | Elevator Contractor | 2 wks | 2020 May 26 8:30 AM | 2020 June 08 5:30 PM
Test and align doors and equipment | Elevator Contractor | 2 wks | 2020 June 09 8:30 AM | 2020 June 22 5:30 PM
Plumbing |  | 90 days | 2020 September 01 1:30 PM | 2021 January 07 12:30 PM
Rough-in plumbing in drywall walls | Plumbing Contractor | 4 wks | 2020 September 29 1:30 PM | 2020 October 28 12:30 PM
Tie-in fire line riser and set valves | Plumbing Contractor | 2 wks | 2020 September 01 1:30 PM | 2020 September 15 12:30 PM
Set plumbing fixtures and trim | Plumbing Contractor | 3 wks | 2020 October 28 1:30 PM | 2020 November 18 12:30 PM
Flush, test, and clean piping and fixtures | Plumbing Contractor | 2 wks | 2020 December 23 1:30 PM | 2021 January 07 12:30 PM
Plumbing works completed |  | 0 days | 2021 January 07 12:30 PM | 2021 January 07 12:30 PM
Electrical Works |  | 139 days | 2020 June 10 8:30 AM | 2020 December 23 12:30 PM
Rough-in electrical in masonry walls | Electric Contractor | 4 wks | 2020 June 10 8:30 AM | 2020 July 07 5:30 PM
Rough-in electrical in drywall walls | Electric Contractor | 4 wks | 2020 September 29 1:30 PM | 2020 October 28 12:30 PM
Pull wire in conduit and set area transformers | Electric Contractor | 3 wks | 2020 October 21 1:30 PM | 2020 November 11 12:30 PM
Install and terminate electrical devices | Electric Contractor | 3 wks | 2020 November 11 1:30 PM | 2020 December 02 12:30 PM
Make electrical terminations for HVAC equipment | Electric Contractor | 2 days | 2020 November 11 1:30 PM | 2020 November 13 12:30 PM
Install light fixtures - test and clean | Electric Contractor | 2 wks | 2020 December 09 1:30 PM | 2020 December 23 12:30 PM
Electrical works completed |  | 0 days | 2020 December 23 12:30 PM | 2020 December 23 12:30 PM
Heating and Ventilating - AC |  | 180 days | 2020 April 28 8:30 AM | 2021 January 07 12:30 PM
Set equipment in mechanical room | HVAC Contractor | 2 wks | 2020 April 28 8:30 AM | 2020 May 11 5:30 PM
Rough-in mechanical in masonry walls | HVAC Contractor | 4 wks | 2020 June 10 8:30 AM | 2020 July 07 5:30 PM
Rough-in mechanical in drywall walls | HVAC Contractor | 2 wks | 2020 September 29 1:30 PM | 2020 October 14 12:30 PM
Install duct in building chase | HVAC Contractor | 3 wks | 2020 September 29 1:30 PM | 2020 October 21 12:30 PM
Set HVAC trim and test and balance system | HVAC Contractor | 4 wks | 2020 December 09 1:30 PM | 2021 January 07 12:30 PM
Final Clean-up and Occupancy |  | 60 days | 2020 November 04 1:30 PM | 2021 January 28 12:30 PM
Install hard tile flooring in common areas | Tile Contractor | 1 wk | 2020 November 04 1:30 PM | 2020 November 11 12:30 PM
Clean hard tile floors | Tile Contractor[50%] | 4 days | 2020 November 11 1:30 PM | 2020 November 17 12:30 PM
Remove debris from building and do final clean-up | Labor Unit | 4 days | 2021 January 21 1:30 PM | 2021 January 27 12:30 PM
Substantial completion date | Superintendent | 1 day | 2021 January 27 1:30 PM | 2021 January 28 12:30 PM
Ready for Occupancy |  | 0 days | 2021 January 28 12:30 PM | 2021 January 28 12:30 PM
Complete Final Inspections |  | 6 days | 2021 January 27 1:30 PM | 2021 February 04 12:30 PM
Complete elevator inspection and certification | Elevator Contractor | 3 days | 2021 January 27 1:30 PM | 2021 February 01 12:30 PM
Perform architect's inspection | Superintendent[50%],Project Management[50%] | 1 day | 2021 February 01 1:30 PM | 2021 February 02 12:30 PM
Perform local building agency inspection | Project Management[50%],Superintendent[50%] | 1 day | 2021 February 02 1:30 PM | 2021 February 03 12:30 PM
Perform Fire Marshal's inspection | Superintendent[50%],Project Management[50%] | 1 day | 2021 February 03 1:30 PM | 2021 February 04 12:30 PM
Final inspection completed |  | 0 days | 2021 February 04 12:30 PM | 2021 February 04 12:30 PM
Project Closure |  | 13 days | 2021 February 04 1:30 PM | 2021 February 23 12:30 PM
Complete punch list items from all inspections | Superintendent[11%],Labor Unit[11%],Plumbing Contractor[11%],Electric Contractor[11%],HVAC Contractor[11%],Drywall Contractor[11%],Carpet Contractor[11%],Paving Contractor[11%],Painting Contractor[11%] | 2 wks | 2021 February 04 1:30 PM | 2021 February 18 12:30 PM
Obtain certificate of occupancy | Project Management | 2 days | 2021 February 18 1:30 PM | 2021 February 22 12:30 PM
Issue final completion documents including warranties | Project Management | 1 day | 2021 February 18 1:30 PM | 2021 February 19 12:30 PM
Issue final request for payment | Project Management[33%],Accounting[33%],General Manager[33%] | 1 day | 2021 February 22 1:30 PM | 2021 February 23 12:30 PM
Payments cleared & Project completed successfully |  | 0 days | 2021 February 23 12:30 PM | 2021 February 23 12:30 PM