## Task_Table
Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
Auto Scheduled | Receiving notice to proceed and sign contract | 3 days | 2019 October 21 8:00 AM | 2019 October 23 5:00 PM |  | 1
Auto Scheduled | Submitting bond and insurance documents | 2 days | 2019 October 24 8:00 AM | 2019 October 25 5:00 PM | 1 | 1
Auto Scheduled | Preparing and submitting project schedule | 2 days | 2019 October 28 8:00 AM | 2019 October 29 5:00 PM | 2 | 1
Auto Scheduled | Preparing and submitting schedule of values | 2 days | 2019 October 30 8:00 AM | 2019 October 31 5:00 PM | 3 | 1
Auto Scheduled | Obtaining building permits | 4 days | 2019 November 01 8:00 AM | 2019 November 06 5:00 PM | 4 | 1
Auto Scheduled | Submitting preliminary shop drawings | 2 wks | 2019 November 07 8:00 AM | 2019 November 20 5:00 PM | 5 | 1
Auto Scheduled | Submitting monthly requests for payment | 1 day | 2019 October 24 8:00 AM | 2019 October 24 5:00 PM | 1 | 1
Auto Scheduled | Submitting shop drawings and order long lead items - steel | 2 wks | 2019 October 25 8:00 AM | 2019 November 07 5:00 PM | 7 | 1
Auto Scheduled | Submitting shop drawings and order long lead items - roofing | 2 wks | 2019 November 21 8:00 AM | 2019 December 04 5:00 PM | 6 | 1
Auto Scheduled | Submitting shop drawings and order long lead items - elevator | 2 wks | 2019 November 21 8:00 AM | 2019 December 04 5:00 PM | 6 | 1
Auto Scheduled | Submitting shop drawings and order long lead items - plumbing | 2 wks | 2019 November 21 8:00 AM | 2019 December 04 5:00 PM | 6 | 1
Auto Scheduled | Submitting shop drawings and order long lead items - electric | 2 wks | 2019 November 21 8:00 AM | 2019 December 04 5:00 PM | 6 | 1
Auto Scheduled | Submitting shop drawings and order long lead items - HVAC | 2 wks | 2019 November 21 8:00 AM | 2019 December 04 5:00 PM | 6 | 1
Auto Scheduled | Detail, fabricate and deliver steel | 12 wks | 2019 November 08 8:00 AM | 2020 January 30 5:00 PM | 8 | 1
Auto Scheduled | Install temporary power | 2 days | 2019 October 24 8:00 AM | 2019 October 25 5:00 PM | 1 | 1
Auto Scheduled | Install temporary water service | 2 days | 2019 October 24 8:00 AM | 2019 October 25 5:00 PM | 1 | 1
Auto Scheduled | Set up site office | 3 days | 2019 October 28 8:00 AM | 2019 October 30 5:00 PM | 15,16 | 1
Auto Scheduled | Set line and grade benchmarks | 3 days | 2019 October 31 8:00 AM | 2019 November 04 5:00 PM | 17 | 1
Auto Scheduled | Prepare site - lay down yard and temporary fencing | 2 days | 2019 November 05 8:00 AM | 2019 November 06 5:00 PM | 18 | 1
Auto Scheduled | Clear and grub site | 3 days | 2019 November 07 8:00 AM | 2019 November 11 5:00 PM | 17,19 | 1
Auto Scheduled | Stone site access and temporary parking area | 2 days | 2019 November 12 8:00 AM | 2019 November 13 5:00 PM | 20,19 | 1
Auto Scheduled | Rough grade site (cut and fill) | 1 wk | 2019 November 14 8:00 AM | 2019 November 20 5:00 PM | 21 | 1
Auto Scheduled | Install storm drainage | 2 wks | 2019 November 21 8:00 AM | 2019 December 04 5:00 PM | 22 | 1
Auto Scheduled | Install exterior fire line and building fire riser | 2 wks | 2019 November 21 8:00 AM | 2019 December 04 5:00 PM | 22 | 1
Auto Scheduled | Perform final site grading | 2 wks | 2019 December 05 8:00 AM | 2019 December 18 5:00 PM | 23FF+1d,24 | 1
Auto Scheduled | Erect building batter boards and layout building | 1 wk | 2019 December 19 8:00 AM | 2019 December 25 5:00 PM | 25 | 1
Auto Scheduled | Excavate foundations | 2 wks | 2019 December 26 8:00 AM | 2020 January 08 5:00 PM | 26 | 1
Auto Scheduled | Excavate elevator pit | 2 days | 2019 December 26 8:00 AM | 2019 December 27 5:00 PM | 26 | 1
Auto Scheduled | Form column piers and spread foundations | 4 days | 2020 January 09 8:00 AM | 2020 January 14 5:00 PM | 27 | 1
Auto Scheduled | Rough-in electric and plumbing in elevator | 4 days | 2019 December 30 8:00 AM | 2020 January 02 5:00 PM | 28 | 1
Auto Scheduled | Form elevator pit walls | 4 days | 2020 January 03 8:00 AM | 2020 January 08 5:00 PM | 30 | 1
Auto Scheduled | Set reinforcing and anchor bolts | 4 days | 2020 January 15 8:00 AM | 2020 January 20 5:00 PM | 29 | 1
Auto Scheduled | Pour column piers and foundations | 5 days | 2020 January 21 8:00 AM | 2020 January 27 5:00 PM | 32 | 1
Auto Scheduled | Pour concrete elevator walls | 1 day | 2020 January 09 8:00 AM | 2020 January 09 5:00 PM | 31 | 1
Auto Scheduled | Cure elevator wall concrete | 7 days | 2020 January 10 8:00 AM | 2020 January 20 5:00 PM | 34 | 1
Auto Scheduled | Cure piers and foundations | 7 days | 2020 January 28 8:00 AM | 2020 February 05 5:00 PM | 33 | 1
Auto Scheduled | Strip wall forms | 1 day | 2020 January 21 8:00 AM | 2020 January 21 5:00 PM | 35 | 1
Auto Scheduled | Strip column piers and foundation forms | 3 days | 2020 February 06 8:00 AM | 2020 February 10 5:00 PM | 36 | 1
Auto Scheduled | Install pneumatic tube in elevator pit | 3 days | 2020 January 22 8:00 AM | 2020 January 24 5:00 PM | 37 | 1
Auto Scheduled | Prepare and pour concrete floor in elevator pit | 1 day | 2020 January 27 8:00 AM | 2020 January 27 5:00 PM | 39 | 1
Auto Scheduled | Erect steel columns, beams and joint - 1st and 2nd floors | 2 wks | 2020 February 11 8:00 AM | 2020 February 24 5:00 PM | 38,14 | 1
Auto Scheduled | Erect steel columns, beams and joint - 3rd floor and roof | 2 wks | 2020 February 25 8:00 AM | 2020 March 09 5:00 PM | 41 | 1
Auto Scheduled | Install miscellaneous iron and bracing - 1st and 2nd floors | 2 wks | 2020 February 25 8:00 AM | 2020 March 09 5:00 PM | 41 | 1
Auto Scheduled | Install miscellaneous iron and bracing - 3rd floor and roof | 2 wks | 2020 March 10 8:00 AM | 2020 March 23 5:00 PM | 42 | 1
Auto Scheduled | Install stairs and miscellaneous iron railing | 2 wks | 2020 March 24 8:00 AM | 2020 April 06 5:00 PM | 44 | 1
Auto Scheduled | Touch-up paint on steel | 1 wk | 2020 April 07 8:00 AM | 2020 April 13 5:00 PM | 45 | 1
Auto Scheduled | Form 2nd floor including all floor openings | 5 days | 2020 April 14 8:00 AM | 2020 April 20 5:00 PM | 46,11,12,13,41 | 1
Auto Scheduled | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 5 days | 2020 February 25 8:00 AM | 2020 March 02 5:00 PM | 41 | 1
Auto Scheduled | Pour 2nd floor slab | 4 days | 2020 April 21 8:00 AM | 2020 April 24 5:00 PM | 48,47 | 1
Auto Scheduled | Cure 2nd floor slab | 7 days | 2020 April 27 8:00 AM | 2020 May 05 5:00 PM | 49 | 1
Auto Scheduled | Strip forms from 2nd floor slab | 2 days | 2020 May 06 8:00 AM | 2020 May 07 5:00 PM | 50 | 1
Auto Scheduled | Form 3rd floor including all floor openings | 5 days | 2020 May 06 8:00 AM | 2020 May 12 5:00 PM | 50 | 1
Auto Scheduled | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 5 days | 2020 May 06 8:00 AM | 2020 May 12 5:00 PM | 50 | 1
Auto Scheduled | Pour 3rd floor slab | 4 days | 2020 May 13 8:00 AM | 2020 May 18 5:00 PM | 53,52 | 1
Auto Scheduled | Cure 3rd floor slab | 7 days | 2020 May 19 8:00 AM | 2020 May 27 5:00 PM | 54 | 1
Auto Scheduled | Strip forms from 3rd floor slab | 2 days | 2020 May 28 8:00 AM | 2020 May 29 5:00 PM | 55 | 1
Auto Scheduled | Form roof slab including all floor openings | 5 days | 2020 May 28 8:00 AM | 2020 June 03 5:00 PM | 55 | 1
Auto Scheduled | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 5 days | 2020 May 28 8:00 AM | 2020 June 03 5:00 PM | 55 | 1
Auto Scheduled | Pour roof slab | 4 days | 2020 June 04 8:00 AM | 2020 June 09 5:00 PM | 58,57 | 1
Auto Scheduled | Cure roof slab | 7 days | 2020 June 10 8:00 AM | 2020 June 18 5:00 PM | 59 | 1
Auto Scheduled | Strip forms from roof slab | 2 days | 2020 June 19 8:00 AM | 2020 June 22 5:00 PM | 60 | 1
Auto Scheduled | Form 1st floor | 4 days | 2020 May 08 8:00 AM | 2020 May 13 5:00 PM | 51 | 1
Auto Scheduled | Install electrical underground | 1 wk | 2020 May 08 8:00 AM | 2020 May 14 5:00 PM | 51 | 1
Auto Scheduled | Install plumbing underground | 1 wk | 2020 May 08 8:00 AM | 2020 May 14 5:00 PM | 51 | 1
Auto Scheduled | Install rebar and in-floor utilities | 4 days | 2020 May 08 8:00 AM | 2020 May 13 5:00 PM | 51 | 1
Auto Scheduled | Pour 1st floor slab | 4 days | 2020 May 15 8:00 AM | 2020 May 20 5:00 PM | 62,65,63,64 | 1
Auto Scheduled | Cure 1st floor slab | 7 days | 2020 May 21 8:00 AM | 2020 May 29 5:00 PM | 66 | 1
Auto Scheduled | Strip forms from 1st floor slab | 2 days | 2020 June 01 8:00 AM | 2020 June 02 5:00 PM | 67 | 1
Auto Scheduled | Install exterior sheathing and metal studs | 3 wks | 2020 June 23 8:00 AM | 2020 July 13 5:00 PM | 56,61 | 1
Auto Scheduled | Rough-in plumbing at toilets and masonry walls | 4 wks | 2020 June 03 8:00 AM | 2020 June 30 5:00 PM | 68,11 | 1
Auto Scheduled | Lay masonry at core, mechanical, and toilets | 4 wks | 2020 March 24 8:00 AM | 2020 April 20 5:00 PM | 43,44 | 1
Auto Scheduled | Install exterior masonry work | 5 wks | 2020 July 14 8:00 AM | 2020 August 17 5:00 PM | 69 | 1
Auto Scheduled | Install roof drains | 2 days | 2020 August 18 8:00 AM | 2020 August 19 5:00 PM | 72 | 1
Auto Scheduled | Install tile in toilet rooms | 2 wks | 2020 July 01 8:00 AM | 2020 July 14 5:00 PM | 70 | 1
Auto Scheduled | Clean masonry | 1 wk | 2020 August 18 8:00 AM | 2020 August 24 5:00 PM | 72 | 1
Auto Scheduled | Clean toilet room tile | 1 wk | 2020 July 15 8:00 AM | 2020 July 21 5:00 PM | 74 | 1
Manually Scheduled | Install flashing at parapet walls | 4 days | 2017 August 20 8:00 AM | 2017 August 23 5:00 PM | 73 | 1
Auto Scheduled | Pour lightweight concrete roof fill | 2 days | 2020 August 20 8:00 AM | 2020 August 21 5:00 PM | 9,73,77 | 1
Auto Scheduled | Install seamless roofing material | 5 days | 2020 August 31 8:00 AM | 2020 September 04 5:00 PM | 78FS+5d | 1
Auto Scheduled | Spread stone ballast on seamless roof | 5 days | 2020 September 07 8:00 AM | 2020 September 11 5:00 PM | 79 | 1
Auto Scheduled | Set rooftop equipment | 2 wks | 2020 September 14 8:00 AM | 2020 September 25 5:00 PM | 80 | 1
Auto Scheduled | Install window wall aluminum and glass | 5 wks | 2020 August 18 8:00 AM | 2020 September 21 5:00 PM | 72 | 1
Auto Scheduled | Install interior stud walls and drywall | 5 wks | 2020 September 22 8:00 AM | 2020 October 26 5:00 PM | 82 | 1
Auto Scheduled | Install interior doors and hardware | 2 wks | 2020 October 27 8:00 AM | 2020 November 09 5:00 PM | 83 | 1
Auto Scheduled | Install store front doors and hardware | 3 wks | 2020 August 18 8:00 AM | 2020 September 07 5:00 PM | 72 | 1
Auto Scheduled | Install millwork and wood trim | 3 wks | 2020 October 27 8:00 AM | 2020 November 16 5:00 PM | 85,83 | 1
Auto Scheduled | Paint walls and woodwork | 4 wks | 2020 November 17 8:00 AM | 2020 December 14 5:00 PM | 86,84 | 1
Auto Scheduled | Install conduit at ceiling plenum space | 3 wks | 2020 September 22 8:00 AM | 2020 October 12 5:00 PM | 82 | 1
Auto Scheduled | Install duct in ceiling plenum space | 3 wks | 2020 October 27 8:00 AM | 2020 November 16 5:00 PM | 83,88 | 1
Auto Scheduled | Install ceiling grid | 2 wks | 2020 November 17 8:00 AM | 2020 November 30 5:00 PM | 83,89 | 1
Auto Scheduled | Install ceiling tile | 2 wks | 2020 December 01 8:00 AM | 2020 December 14 5:00 PM | 90 | 1
Auto Scheduled | Hang wallpaper | 2 wks | 2020 December 01 8:00 AM | 2020 December 14 5:00 PM | 90 | 1
Auto Scheduled | Install building carpet | 4 wks | 2020 December 15 8:00 AM | 2021 January 11 5:00 PM | 87 | 1
Auto Scheduled | Install hardware and accessories | 3 wks | 2020 December 15 8:00 AM | 2021 January 04 5:00 PM | 87 | 1
Auto Scheduled | Complete interior and exterior sod and plantings | 2 wks | 2020 December 15 8:00 AM | 2020 December 28 5:00 PM | 87 | 1
Auto Scheduled | Pave, curb, and stripe parking lot | 2 wks | 2020 December 29 8:00 AM | 2021 January 11 5:00 PM | 95 | 1
Auto Scheduled | Set elevator equipment in shafts | 4 wks | 2020 April 21 8:00 AM | 2020 May 18 5:00 PM | 71,40,10 | 1
Auto Scheduled | Set equipment in mechanical room | 2 wks | 2020 May 19 8:00 AM | 2020 June 01 5:00 PM | 97 | 1
Auto Scheduled | Test and align doors and equipment | 2 wks | 2020 June 02 8:00 AM | 2020 June 15 5:00 PM | 98 | 1
Auto Scheduled | Rough-in plumbing in drywall walls | 4 wks | 2020 September 22 8:00 AM | 2020 October 19 5:00 PM | 82 | 1
Auto Scheduled | Tie-in fire line riser and set valves | 2 wks | 2020 August 25 8:00 AM | 2020 September 07 5:00 PM | 75 | 1
Auto Scheduled | Set plumbing fixtures and trim | 3 wks | 2020 October 20 8:00 AM | 2020 November 09 5:00 PM | 76,100,70 | 1
Auto Scheduled | Flush, test, and clean piping and fixtures | 2 wks | 2020 December 15 8:00 AM | 2020 December 28 5:00 PM | 87,101,102 | 1
Auto Scheduled | Rough-in electrical in masonry walls | 4 wks | 2020 June 03 8:00 AM | 2020 June 30 5:00 PM | 68,12 | 1
Auto Scheduled | Rough-in electrical in drywall walls | 4 wks | 2020 September 22 8:00 AM | 2020 October 19 5:00 PM | 82 | 1
Auto Scheduled | Pull wire in conduit and set area transformers | 3 wks | 2020 October 13 8:00 AM | 2020 November 02 5:00 PM | 104,88 | 1
Auto Scheduled | Install and terminate electrical devices | 3 wks | 2020 November 03 8:00 AM | 2020 November 23 5:00 PM | 106,105 | 1
Auto Scheduled | Make electrical terminations for HVAC equipment | 2 days | 2020 November 03 8:00 AM | 2020 November 04 5:00 PM | 106,81 | 1
Auto Scheduled | Install light fixtures - test and clean | 2 wks | 2020 December 01 8:00 AM | 2020 December 14 5:00 PM | 90,107 | 1
Auto Scheduled | Set equipment in mechanical room | 2 wks | 2020 April 21 8:00 AM | 2020 May 04 5:00 PM | 71,13 | 1
Auto Scheduled | Rough-in mechanical in masonry walls | 4 wks | 2020 June 03 8:00 AM | 2020 June 30 5:00 PM | 68 | 1
Auto Scheduled | Rough-in mechanical in drywall walls | 2 wks | 2020 September 22 8:00 AM | 2020 October 05 5:00 PM | 82 | 1
Auto Scheduled | Install duct in building chase | 3 wks | 2020 September 22 8:00 AM | 2020 October 12 5:00 PM | 110,111,82 | 1
Auto Scheduled | Set HVAC trim and test and balance system | 4 wks | 2020 December 01 8:00 AM | 2020 December 28 5:00 PM | 90,113,108 | 1
Auto Scheduled | Install hard tile flooring in common areas | 1 wk | 2020 October 27 8:00 AM | 2020 November 02 5:00 PM | 83 | 1
Auto Scheduled | Clean hard tile floors | 4 days | 2020 November 03 8:00 AM | 2020 November 06 5:00 PM | 115 | 1
Auto Scheduled | Remove debris from building and do final clean-up | 4 days | 2021 January 12 8:00 AM | 2021 January 15 5:00 PM | 93,92,94,95,103,109,91,116 | 1
Auto Scheduled | Substantial completion date | 1 day | 2021 January 18 8:00 AM | 2021 January 18 5:00 PM | 117 | 1
Auto Scheduled | Complete elevator inspection and certification | 3 days | 2021 January 18 8:00 AM | 2021 January 20 5:00 PM | 117,99 | 1
Auto Scheduled | Perform architect's inspection | 1 day | 2021 January 21 8:00 AM | 2021 January 21 5:00 PM | 117,96,119 | 1
Auto Scheduled | Perform local building agency inspection | 1 day | 2021 January 22 8:00 AM | 2021 January 22 5:00 PM | 120 | 1
Auto Scheduled | Perform Fire Marshal's inspection | 1 day | 2021 January 25 8:00 AM | 2021 January 25 5:00 PM | 121 | 1
Auto Scheduled | Complete punch list items from all inspections | 2 wks | 2021 January 26 8:00 AM | 2021 February 08 5:00 PM | 122 | 1
Auto Scheduled | Obtain certificate of occupancy | 2 days | 2021 February 09 8:00 AM | 2021 February 10 5:00 PM | 123 | 1
Auto Scheduled | Issue final completion documents including warranties | 1 day | 2021 February 09 8:00 AM | 2021 February 09 5:00 PM | 123 | 1
Auto Scheduled | Issue final request for payment | 1 day | 2021 February 11 8:00 AM | 2021 February 11 5:00 PM | 124,125 | 1

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
0 |  |  | Work |  |  |  |  | 100% | $0.00/h | 0
1 | General Management | G | Work |  |  |  |  | 100% | $0.00/h | 0
2 | Project Management | P | Work |  |  |  |  | 100% | $0.00/h | 0
3 | Procurement | P | Work |  |  |  |  | 100% | $0.00/h | 0
4 | Scheduler | S | Work |  |  |  |  | 100% | $0.00/h | 0
5 | Accounting | A | Work |  |  |  |  | 100% | $0.00/h | 0
6 | Superintendent | S | Work |  |  |  |  | 100% | $0.00/h | 0
7 | Survey Crew | S | Work |  |  |  |  | 100% | $0.00/h | 0
8 | Rough Carpenter Crew | R | Work |  |  |  |  | 100% | $0.00/h | 0
9 | Labor Crew | L | Work |  |  |  |  | 100% | $0.00/h | 0
10 | Concrete Crew | C | Work |  |  |  |  | 100% | $0.00/h | 0
11 | Finish Carpenter Crew | F | Work |  |  |  |  | 100% | $0.00/h | 0
12 | Site Grading Contractor | S | Work |  |  |  |  | 100% | $0.00/h | 0
13 | Plumbing Contractor | P | Work |  |  |  |  | 100% | $0.00/h | 0
14 | Plumbing Contractor Management | P | Work |  |  |  |  | 100% | $0.00/h | 0
15 | Electric Contractor | E | Work |  |  |  |  | 100% | $0.00/h | 0
16 | Electric Contractor Management | E | Work |  |  |  |  | 100% | $0.00/h | 0
17 | HVAC Contractor | H | Work |  |  |  |  | 100% | $0.00/h | 0
18 | HVAC Contractor Management | H | Work |  |  |  |  | 100% | $0.00/h | 0
19 | Elevator Contractor | E | Work |  |  |  |  | 100% | $0.00/h | 0
20 | Elevator Contractor Management | E | Work |  |  |  |  | 100% | $0.00/h | 0
21 | Steel Erection Contractor | S | Work |  |  |  |  | 100% | $0.00/h | 0
22 | Steel Erection Contractor Management | S | Work |  |  |  |  | 100% | $0.00/h | 0
23 | Drywall Contractor | D | Work |  |  |  |  | 100% | $0.00/h | 0
24 | Masonry Contractor | M | Work |  |  |  |  | 100% | $0.00/h | 0
25 | Tile Contractor | T | Work |  |  |  |  | 100% | $0.00/h | 0
26 | Roofing Contractor | R | Work |  |  |  |  | 100% | $0.00/h | 0
27 | Roofing Contractor Management | R | Work |  |  |  |  | 100% | $0.00/h | 0
28 | Window Contractor | W | Work |  |  |  |  | 100% | $0.00/h | 0
29 | Carpet Contractor | C | Work |  |  |  |  | 100% | $0.00/h | 0
30 | Landscape Contractor | L | Work |  |  |  |  | 100% | $0.00/h | 0
31 | Paving Contractor | P | Work |  |  |  |  | 100% | $0.00/h | 0
32 | Painting Contractor | P | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Receive notice to proceed and sign contract | General Management | 0 | 24h | 100%
Submit bond and insurance documents | Project Management | 0 | 16h | 100%
Submit bond and insurance documents | General Management | 0 | 4h | 25%
Prepare and submit project schedule | Project Management | 0 | 4h | 25%
Prepare and submit project schedule | Scheduler | 0 | 16h | 100%
Prepare and submit schedule of values | General Management | 0 | 1.6h | 10%
Prepare and submit schedule of values | Project Management | 0 | 16h | 100%
Obtain building permits | Project Management | 0 | 16h | 50%
Obtain building permits | Procurement | 0 | 16h | 50%
Submit preliminary shop drawings | Project Management | 0 | 40h | 50%
Submit preliminary shop drawings | Procurement | 0 | 40h | 50%
Submit shop drawings and order long lead items - steel | Steel Erection Contractor Management | 0 | 80h | 100%
Submit shop drawings and order long lead items - roofing | Roofing Contractor Management | 0 | 80h | 100%
Submit shop drawings and order long lead items - elevator | Elevator Contractor Management | 0 | 80h | 100%
Submit shop drawings and order long lead items - plumbing | Plumbing Contractor Management | 0 | 80h | 100%
Submit shop drawings and order long lead items - electric | Electric Contractor Management | 0 | 80h | 100%
Submit shop drawings and order long lead items - HVAC | HVAC Contractor Management | 0 | 80h | 100%
Detail, fabricate and deliver steel | Steel Erection Contractor Management | 0 | 240h | 50%
Detail, fabricate and deliver steel | Steel Erection Contractor | 0 | 240h | 50%
Install temporary power | Electric Contractor | 0 | 16h | 100%
Install temporary water service | Plumbing Contractor | 0 | 16h | 100%
Set up site office | Superintendent | 0 | 24h | 100%
Set up site office | Labor Crew | 0 | 2.4h | 10%
Set line and grade benchmarks | Survey Crew | 0 | 24h | 100%
Prepare site - lay down yard and temporary fencing | Site Grading Contractor | 0 | 16h | 100%
Prepare site - lay down yard and temporary fencing | Labor Crew | 0 | 1.6h | 10%
Clear and grub site | Site Grading Contractor | 0 | 24h | 100%
Stone site access and temporary parking area | Site Grading Contractor | 0 | 16h | 100%
Rough grade site (cut and fill) | Site Grading Contractor | 0 | 40h | 100%
Install storm drainage | Site Grading Contractor | 0 | 80h | 100%
Install exterior fire line and building fire riser | Plumbing Contractor | 0 | 80h | 100%
Perform final site grading | Site Grading Contractor | 0 | 80h | 100%
Erect building batter boards and layout building | Survey Crew | 0 | 40h | 100%
Excavate foundations | Site Grading Contractor | 0 | 40h | 50%
Excavate elevator pit | Site Grading Contractor | 0 | 16h | 100%
Form column piers and spread foundations | Rough Carpenter Crew | 0 | 32h | 100%
Rough-in electric and plumbing in elevator | Plumbing Contractor | 0 | 32h | 100%
Rough-in electric and plumbing in elevator | Electric Contractor | 0 | 32h | 100%
Form elevator pit walls | Rough Carpenter Crew | 0 | 32h | 100%
Set reinforcing and anchor bolts | Rough Carpenter Crew | 0 | 32h | 100%
Pour column piers and foundations | Concrete Crew | 0 | 40h | 100%
Pour concrete elevator walls | Concrete Crew | 0 | 8h | 100%
Cure elevator wall concrete | Labor Crew | 0 | 5.6h | 10%
Cure piers and foundations | Labor Crew | 0 | 5.6h | 10%
Strip wall forms | Labor Crew | 0 | 0.8h | 10%
Strip column piers and foundation forms | Labor Crew | 0 | 24h | 100%
Install pneumatic tube in elevator pit | Elevator Contractor | 0 | 24h | 100%
Prepare and pour concrete floor in elevator pit | Concrete Crew | 0 | 8h | 100%
Erect steel columns, beams and joint - 1st and 2nd floors | Steel Erection Contractor | 0 | 80h | 100%
Erect steel columns, beams and joint - 3rd floor and roof | Steel Erection Contractor | 0 | 80h | 100%
Install miscellaneous iron and bracing - 1st and 2nd floors | Steel Erection Contractor | 0 | 60h | 75%
Install miscellaneous iron and bracing - 3rd floor and roof | Steel Erection Contractor | 0 | 60h | 75%
Install stairs and miscellaneous iron railing | Steel Erection Contractor | 0 | 40h | 50%
Touch-up paint on steel | Steel Erection Contractor | 0 | 8h | 20%
Form 2nd floor including all floor openings | Rough Carpenter Crew | 0 | 40h | 100%
Form 2nd floor including all floor openings | Labor Crew | 0 | 8h | 20%
Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Labor Crew | 0 | 13.2h | 33%
Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Plumbing Contractor | 0 | 13.2h | 33%
Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Electric Contractor | 0 | 13.2h | 33%
Pour 2nd floor slab | Concrete Crew | 0 | 32h | 100%
Cure 2nd floor slab | Labor Crew | 0 | 5.6h | 10%
Strip forms from 2nd floor slab | Labor Crew | 0 | 16h | 100%
Form 3rd floor including all floor openings | Rough Carpenter Crew | 0 | 20h | 50%
Form 3rd floor including all floor openings | Labor Crew | 0 | 8h | 20%
Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Labor Crew | 0 | 13.2h | 33%
Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Plumbing Contractor | 0 | 13.2h | 33%
Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Electric Contractor | 0 | 13.2h | 33%
Pour 3rd floor slab | Concrete Crew | 0 | 32h | 100%
Cure 3rd floor slab | Labor Crew | 0 | 5.6h | 10%
Strip forms from 3rd floor slab | Labor Crew | 0 | 16h | 100%
Form roof slab including all floor openings | Rough Carpenter Crew | 0 | 40h | 100%
Form roof slab including all floor openings | Labor Crew | 0 | 8h | 20%
Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Labor Crew | 0 | 13.2h | 33%
Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Plumbing Contractor | 0 | 13.2h | 33%
Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Electric Contractor | 0 | 13.2h | 33%
Pour roof slab | Concrete Crew | 0 | 32h | 100%
Cure roof slab | Labor Crew | 0 | 5.6h | 10%
Strip forms from roof slab | Labor Crew | 0 | 16h | 100%
Form 1st floor | Rough Carpenter Crew | 0 | 32h | 100%
Install electrical underground | Electric Contractor | 0 | 40h | 100%
Install plumbing underground | Plumbing Contractor | 0 | 40h | 100%
Install rebar and in-floor utilities | Labor Crew | 0 | 10.57h | 33%
Install rebar and in-floor utilities | Plumbing Contractor | 0 | 10.57h | 33%
Install rebar and in-floor utilities | Electric Contractor | 0 | 10.57h | 33%
Pour 1st floor slab | Concrete Crew | 0 | 32h | 100%
Cure 1st floor slab | Labor Crew | 0 | 5.6h | 10%
Strip forms from 1st floor slab | Labor Crew | 0 | 16h | 100%
Install exterior sheathing and metal studs | Drywall Contractor | 0 | 120h | 100%
Rough-in plumbing at toilets and masonry walls | Plumbing Contractor | 0 | 160h | 100%
Lay masonry at core, mechanical, and toilets | Masonry Contractor | 0 | 160h | 100%
Install exterior masonry work | Masonry Contractor | 0 | 200h | 100%
Install roof drains | Roofing Contractor | 0 | 16h | 100%
Install tile in toilet rooms | Tile Contractor | 0 | 80h | 100%
Clean masonry | Masonry Contractor | 0 | 20h | 50%
Clean toilet room tile | Tile Contractor | 0 | 20h | 50%
Install flashing at parapet walls | Roofing Contractor | 0 | 32h | 100%
Pour lightweight concrete roof fill | Roofing Contractor | 0 | 16h | 100%
Install seamless roofing material | Roofing Contractor | 0 | 40h | 100%
Spread stone ballast on seamless roof | Roofing Contractor | 0 | 40h | 100%
Set rooftop equipment | HVAC Contractor | 0 | 80h | 100%
Install window wall aluminum and glass | Window Contractor | 0 | 200h | 100%
Install interior stud walls and drywall | Drywall Contractor | 0 | 200h | 100%
Install interior doors and hardware | Finish Carpenter Crew | 0 | 80h | 100%
Install store front doors and hardware | Window Contractor | 0 | 120h | 100%
Install millwork and wood trim | Finish Carpenter Crew | 0 | 120h | 100%
Paint walls and woodwork | Painting Contractor | 0 | 160h | 100%
Install conduit at ceiling plenum space | Electric Contractor | 0 | 120h | 100%
Install duct in ceiling plenum space | HVAC Contractor | 0 | 120h | 100%
Install ceiling grid | Drywall Contractor | 0 | 80h | 100%
Install ceiling tile | Drywall Contractor | 0 | 80h | 100%
Hang wallpaper | Painting Contractor | 0 | 80h | 100%
Install building carpet | Carpet Contractor | 0 | 160h | 100%
Install hardware and accessories | Finish Carpenter Crew | 0 | 120h | 100%
Complete interior and exterior sod and plantings | Landscape Contractor | 0 | 80h | 100%
Pave, curb, and stripe parking lot | Paving Contractor | 0 | 80h | 100%
Set elevator equipment in shafts | Elevator Contractor | 0 | 160h | 100%
Set equipment in mechanical room | Elevator Contractor | 0 | 80h | 100%
Test and align doors and equipment | Elevator Contractor | 0 | 80h | 100%
Rough-in plumbing in drywall walls | Plumbing Contractor | 0 | 160h | 100%
Tie-in fire line riser and set valves | Plumbing Contractor | 0 | 80h | 100%
Set plumbing fixtures and trim | Plumbing Contractor | 0 | 120h | 100%
Flush, test, and clean piping and fixtures | Plumbing Contractor | 0 | 80h | 100%
Rough-in electrical in masonry walls | Electric Contractor | 0 | 160h | 100%
Rough-in electrical in drywall walls | Electric Contractor | 0 | 160h | 100%
Pull wire in conduit and set area transformers | Electric Contractor | 0 | 120h | 100%
Install and terminate electrical devices | Electric Contractor | 0 | 120h | 100%
Make electrical terminations for HVAC equipment | Electric Contractor | 0 | 16h | 100%
Install light fixtures - test and clean | Electric Contractor | 0 | 80h | 100%
Set equipment in mechanical room | HVAC Contractor | 0 | 80h | 100%
Rough-in mechanical in masonry walls | HVAC Contractor | 0 | 160h | 100%
Rough-in mechanical in drywall walls | HVAC Contractor | 0 | 80h | 100%
Install duct in building chase | HVAC Contractor | 0 | 120h | 100%
Set HVAC trim and test and balance system | HVAC Contractor | 0 | 160h | 100%
Install hard tile flooring in common areas | Tile Contractor | 0 | 40h | 100%
Clean hard tile floors | Tile Contractor | 0 | 16h | 50%
Remove debris from building and do final clean-up | Labor Crew | 0 | 32h | 100%
Substantial completion date | Superintendent | 0 | 8h | 100%
Complete elevator inspection and certification | Elevator Contractor | 0 | 24h | 100%
Perform architect's inspection | Superintendent | 0 | 4h | 50%
Perform architect's inspection | Project Management | 0 | 4h | 50%
Perform local building agency inspection | Project Management | 0 | 4h | 50%
Perform local building agency inspection | Superintendent | 0 | 4h | 50%
Perform Fire Marshal's inspection | Superintendent | 0 | 4h | 50%
Perform Fire Marshal's inspection | Project Management | 0 | 4h | 50%
Complete punch list items from all inspections | Superintendent | 0 | 8.8h | 11%
Complete punch list items from all inspections | Labor Crew | 0 | 8.8h | 11%
Complete punch list items from all inspections | Plumbing Contractor | 0 | 8.8h | 11%
Complete punch list items from all inspections | Electric Contractor | 0 | 8.8h | 11%
Complete punch list items from all inspections | HVAC Contractor | 0 | 8.8h | 11%
Complete punch list items from all inspections | Drywall Contractor | 0 | 8.8h | 11%
Complete punch list items from all inspections | Carpet Contractor | 0 | 8.8h | 11%
Complete punch list items from all inspections | Paving Contractor | 0 | 8.8h | 11%
Complete punch list items from all inspections | Painting Contractor | 0 | 8.8h | 11%
Obtain certificate of occupancy | Project Management | 0 | 16h | 100%
Issue final completion documents including warranties | Project Management | 0 | 8h | 100%
Issue final request for payment | Project Management | 0 | 2.63h | 33%
Issue final request for payment | Accounting | 0 | 2.63h | 33%
Issue final request for payment | General Management | 0 | 2.63h | 33%