## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
0 | Yes | Auto Scheduled | Commercial Office Space Construction | 909 days | 2017 August 20 8:00 AM | 2021 February 11 5:00 PM |  | 0
1 | Yes | Auto Scheduled | General Conditions | 23 days | 2019 October 21 8:00 AM | 2019 November 20 5:00 PM |  | 1
2 | Yes | Auto Scheduled | Receive notice to proceed and sign contract | 3 days | 2019 October 21 8:00 AM | 2019 October 23 5:00 PM |  | 2
3 | Yes | Auto Scheduled | Submit bond and insurance documents | 2 days | 2019 October 24 8:00 AM | 2019 October 25 5:00 PM | 2 | 2
4 | Yes | Auto Scheduled | Prepare and submit project schedule | 2 days | 2019 October 28 8:00 AM | 2019 October 29 5:00 PM | 3 | 2
5 | Yes | Auto Scheduled | Prepare and submit schedule of values | 2 days | 2019 October 30 8:00 AM | 2019 October 31 5:00 PM | 4 | 2
6 | Yes | Auto Scheduled | Obtain building permits | 4 days | 2019 November 01 8:00 AM | 2019 November 06 5:00 PM | 5 | 2
7 | Yes | Auto Scheduled | Submit preliminary shop drawings | 2 wks | 2019 November 07 8:00 AM | 2019 November 20 5:00 PM | 6 | 2
8 | Yes | Auto Scheduled | Submit monthly requests for payment | 1 day | 2019 October 24 8:00 AM | 2019 October 24 5:00 PM | 2 | 2
9 | Yes | Auto Scheduled | Long Lead Procurement | 70 days | 2019 October 25 8:00 AM | 2020 January 30 5:00 PM |  | 1
10 | Yes | Auto Scheduled | Submit shop drawings and order long lead items - steel | 2 wks | 2019 October 25 8:00 AM | 2019 November 07 5:00 PM | 8 | 2
11 | Yes | Auto Scheduled | Submit shop drawings and order long lead items - roofing | 2 wks | 2019 November 21 8:00 AM | 2019 December 04 5:00 PM | 7 | 2
12 | Yes | Auto Scheduled | Submit shop drawings and order long lead items - elevator | 2 wks | 2019 November 21 8:00 AM | 2019 December 04 5:00 PM | 7 | 2
13 | Yes | Auto Scheduled | Submit shop drawings and order long lead items - plumbing | 2 wks | 2019 November 21 8:00 AM | 2019 December 04 5:00 PM | 7 | 2
14 | Yes | Auto Scheduled | Submit shop drawings and order long lead items - electric | 2 wks | 2019 November 21 8:00 AM | 2019 December 04 5:00 PM | 7 | 2
15 | Yes | Auto Scheduled | Submit shop drawings and order long lead items - HVAC | 2 wks | 2019 November 21 8:00 AM | 2019 December 04 5:00 PM | 7 | 2
16 | Yes | Auto Scheduled | Detail, fabricate and deliver steel | 12 wks | 2019 November 08 8:00 AM | 2020 January 30 5:00 PM | 10 | 2
17 | Yes | Auto Scheduled | Mobilize on Site | 10 days | 2019 October 24 8:00 AM | 2019 November 06 5:00 PM |  | 1
18 | Yes | Auto Scheduled | Install temporary power | 2 days | 2019 October 24 8:00 AM | 2019 October 25 5:00 PM | 2 | 2
19 | Yes | Auto Scheduled | Install temporary water service | 2 days | 2019 October 24 8:00 AM | 2019 October 25 5:00 PM | 2 | 2
20 | Yes | Auto Scheduled | Set up site office | 3 days | 2019 October 28 8:00 AM | 2019 October 30 5:00 PM | 18,19 | 2
21 | Yes | Auto Scheduled | Set line and grade benchmarks | 3 days | 2019 October 31 8:00 AM | 2019 November 04 5:00 PM | 20 | 2
22 | Yes | Auto Scheduled | Prepare site - lay down yard and temporary fencing | 2 days | 2019 November 05 8:00 AM | 2019 November 06 5:00 PM | 21 | 2
23 | Yes | Auto Scheduled | Site Grading and Utilities | 35 days | 2019 November 07 8:00 AM | 2019 December 25 5:00 PM |  | 1
24 | Yes | Auto Scheduled | Clear and grub site | 3 days | 2019 November 07 8:00 AM | 2019 November 11 5:00 PM | 20,22 | 2
25 | Yes | Auto Scheduled | Stone site access and temporary parking area | 2 days | 2019 November 12 8:00 AM | 2019 November 13 5:00 PM | 24,22 | 2
26 | Yes | Auto Scheduled | Rough grade site (cut and fill) | 1 wk | 2019 November 14 8:00 AM | 2019 November 20 5:00 PM | 25 | 2
27 | Yes | Auto Scheduled | Install storm drainage | 2 wks | 2019 November 21 8:00 AM | 2019 December 04 5:00 PM | 26 | 2
28 | Yes | Auto Scheduled | Install exterior fire line and building fire riser | 2 wks | 2019 November 21 8:00 AM | 2019 December 04 5:00 PM | 26 | 2
29 | Yes | Auto Scheduled | Perform final site grading | 2 wks | 2019 December 05 8:00 AM | 2019 December 18 5:00 PM | 27FF+1d,28 | 2
30 | Yes | Auto Scheduled | Erect building batter boards and layout building | 1 wk | 2019 December 19 8:00 AM | 2019 December 25 5:00 PM | 29 | 2
31 | Yes | Auto Scheduled | Excavation and Foundations | 33 days | 2019 December 26 8:00 AM | 2020 February 10 5:00 PM |  | 1
32 | Yes | Auto Scheduled | Excavate foundations | 2 wks | 2019 December 26 8:00 AM | 2020 January 08 5:00 PM | 30 | 2
33 | Yes | Auto Scheduled | Excavate elevator pit | 2 days | 2019 December 26 8:00 AM | 2019 December 27 5:00 PM | 30 | 2
34 | Yes | Auto Scheduled | Form column piers and spread foundations | 4 days | 2020 January 09 8:00 AM | 2020 January 14 5:00 PM | 32 | 2
35 | Yes | Auto Scheduled | Rough-in electric and plumbing in elevator | 4 days | 2019 December 30 8:00 AM | 2020 January 02 5:00 PM | 33 | 2
36 | Yes | Auto Scheduled | Form elevator pit walls | 4 days | 2020 January 03 8:00 AM | 2020 January 08 5:00 PM | 35 | 2
37 | Yes | Auto Scheduled | Set reinforcing and anchor bolts | 4 days | 2020 January 15 8:00 AM | 2020 January 20 5:00 PM | 34 | 2
38 | Yes | Auto Scheduled | Pour column piers and foundations | 5 days | 2020 January 21 8:00 AM | 2020 January 27 5:00 PM | 37 | 2
39 | Yes | Auto Scheduled | Pour concrete elevator walls | 1 day | 2020 January 09 8:00 AM | 2020 January 09 5:00 PM | 36 | 2
40 | Yes | Auto Scheduled | Cure elevator wall concrete | 7 days | 2020 January 10 8:00 AM | 2020 January 20 5:00 PM | 39 | 2
41 | Yes | Auto Scheduled | Cure piers and foundations | 7 days | 2020 January 28 8:00 AM | 2020 February 05 5:00 PM | 38 | 2
42 | Yes | Auto Scheduled | Strip wall forms | 1 day | 2020 January 21 8:00 AM | 2020 January 21 5:00 PM | 40 | 2
43 | Yes | Auto Scheduled | Strip column piers and foundation forms | 3 days | 2020 February 06 8:00 AM | 2020 February 10 5:00 PM | 41 | 2
44 | Yes | Auto Scheduled | Install pneumatic tube in elevator pit | 3 days | 2020 January 22 8:00 AM | 2020 January 24 5:00 PM | 42 | 2
45 | Yes | Auto Scheduled | Prepare and pour concrete floor in elevator pit | 1 day | 2020 January 27 8:00 AM | 2020 January 27 5:00 PM | 44 | 2
46 | Yes | Auto Scheduled | Column Erection and Miscellaneous steel works | 45 days | 2020 February 11 8:00 AM | 2020 April 13 5:00 PM |  | 1
47 | Yes | Auto Scheduled | Erect steel columns, beams and joint - 1st and 2nd floors | 2 wks | 2020 February 11 8:00 AM | 2020 February 24 5:00 PM | 43,16 | 2
48 | Yes | Auto Scheduled | Erect steel columns, beams and joint - 3rd floor and roof | 2 wks | 2020 February 25 8:00 AM | 2020 March 09 5:00 PM | 47 | 2
49 | Yes | Auto Scheduled | Install miscellaneous iron and bracing - 1st and 2nd floors | 2 wks | 2020 February 25 8:00 AM | 2020 March 09 5:00 PM | 47 | 2
50 | Yes | Auto Scheduled | Install miscellaneous iron and bracing - 3rd floor and roof | 2 wks | 2020 March 10 8:00 AM | 2020 March 23 5:00 PM | 48 | 2
51 | Yes | Auto Scheduled | Install stairs and miscellaneous iron railing | 2 wks | 2020 March 24 8:00 AM | 2020 April 06 5:00 PM | 50 | 2
52 | Yes | Auto Scheduled | Touch-up paint on steel | 1 wk | 2020 April 07 8:00 AM | 2020 April 13 5:00 PM | 51 | 2
53 | Yes | Auto Scheduled | Forming, Pouring, & Curing - Floors and Roof | 85 days | 2020 February 25 8:00 AM | 2020 June 22 5:00 PM |  | 1
54 | Yes | Auto Scheduled | Form 2nd floor including all floor openings | 5 days | 2020 April 14 8:00 AM | 2020 April 20 5:00 PM | 52,13,14,15,47 | 2
55 | Yes | Auto Scheduled | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 5 days | 2020 February 25 8:00 AM | 2020 March 02 5:00 PM | 47 | 2
56 | Yes | Auto Scheduled | Pour 2nd floor slab | 4 days | 2020 April 21 8:00 AM | 2020 April 24 5:00 PM | 55,54 | 2
57 | Yes | Auto Scheduled | Cure 2nd floor slab | 7 days | 2020 April 27 8:00 AM | 2020 May 05 5:00 PM | 56 | 2
58 | Yes | Auto Scheduled | Strip forms from 2nd floor slab | 2 days | 2020 May 06 8:00 AM | 2020 May 07 5:00 PM | 57 | 2
59 | Yes | Auto Scheduled | Form 3rd floor including all floor openings | 5 days | 2020 May 06 8:00 AM | 2020 May 12 5:00 PM | 57 | 2
60 | Yes | Auto Scheduled | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 5 days | 2020 May 06 8:00 AM | 2020 May 12 5:00 PM | 57 | 2
61 | Yes | Auto Scheduled | Pour 3rd floor slab | 4 days | 2020 May 13 8:00 AM | 2020 May 18 5:00 PM | 60,59 | 2
62 | Yes | Auto Scheduled | Cure 3rd floor slab | 7 days | 2020 May 19 8:00 AM | 2020 May 27 5:00 PM | 61 | 2
63 | Yes | Auto Scheduled | Strip forms from 3rd floor slab | 2 days | 2020 May 28 8:00 AM | 2020 May 29 5:00 PM | 62 | 2
64 | Yes | Auto Scheduled | Form roof slab including all floor openings | 5 days | 2020 May 28 8:00 AM | 2020 June 03 5:00 PM | 62 | 2
65 | Yes | Auto Scheduled | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | 5 days | 2020 May 28 8:00 AM | 2020 June 03 5:00 PM | 62 | 2
66 | Yes | Auto Scheduled | Pour roof slab | 4 days | 2020 June 04 8:00 AM | 2020 June 09 5:00 PM | 65,64 | 2
67 | Yes | Auto Scheduled | Cure roof slab | 7 days | 2020 June 10 8:00 AM | 2020 June 18 5:00 PM | 66 | 2
68 | Yes | Auto Scheduled | Strip forms from roof slab | 2 days | 2020 June 19 8:00 AM | 2020 June 22 5:00 PM | 67 | 2
69 | Yes | Auto Scheduled | Form 1st floor | 4 days | 2020 May 08 8:00 AM | 2020 May 13 5:00 PM | 58 | 2
70 | Yes | Auto Scheduled | Install electrical underground | 1 wk | 2020 May 08 8:00 AM | 2020 May 14 5:00 PM | 58 | 2
71 | Yes | Auto Scheduled | Install plumbing underground | 1 wk | 2020 May 08 8:00 AM | 2020 May 14 5:00 PM | 58 | 2
72 | Yes | Auto Scheduled | Install rebar and in-floor utilities | 4 days | 2020 May 08 8:00 AM | 2020 May 13 5:00 PM | 58 | 2
73 | Yes | Auto Scheduled | Pour 1st floor slab | 4 days | 2020 May 15 8:00 AM | 2020 May 20 5:00 PM | 69,72,70,71 | 2
74 | Yes | Auto Scheduled | Cure 1st floor slab | 7 days | 2020 May 21 8:00 AM | 2020 May 29 5:00 PM | 73 | 2
75 | Yes | Auto Scheduled | Strip forms from 1st floor slab | 2 days | 2020 June 01 8:00 AM | 2020 June 02 5:00 PM | 74 | 2
76 | Yes | Auto Scheduled | Carpentry Work | 15 days | 2020 June 23 8:00 AM | 2020 July 13 5:00 PM |  | 1
77 | Yes | Auto Scheduled | Install exterior sheathing and metal studs | 3 wks | 2020 June 23 8:00 AM | 2020 July 13 5:00 PM | 63,68 | 2
78 | Yes | Auto Scheduled | Masonry Work | 110 days | 2020 March 24 8:00 AM | 2020 August 24 5:00 PM |  | 1
79 | Yes | Auto Scheduled | Rough-in plumbing at toilets and masonry walls | 4 wks | 2020 June 03 8:00 AM | 2020 June 30 5:00 PM | 75,13 | 2
80 | Yes | Auto Scheduled | Lay masonry at core, mechanical, and toilets | 4 wks | 2020 March 24 8:00 AM | 2020 April 20 5:00 PM | 49,50 | 2
81 | Yes | Auto Scheduled | Install exterior masonry work | 5 wks | 2020 July 14 8:00 AM | 2020 August 17 5:00 PM | 77 | 2
82 | Yes | Auto Scheduled | Install roof drains | 2 days | 2020 August 18 8:00 AM | 2020 August 19 5:00 PM | 81 | 2
83 | Yes | Auto Scheduled | Install tile in toilet rooms | 2 wks | 2020 July 01 8:00 AM | 2020 July 14 5:00 PM | 79 | 2
84 | Yes | Auto Scheduled | Clean masonry | 1 wk | 2020 August 18 8:00 AM | 2020 August 24 5:00 PM | 81 | 2
85 | Yes | Auto Scheduled | Clean toilet room tile | 1 wk | 2020 July 15 8:00 AM | 2020 July 21 5:00 PM | 83 | 2
86 | Yes | Auto Scheduled | Roofing | 810 days | 2017 August 20 8:00 AM | 2020 September 25 5:00 PM |  | 1
87 | Yes | Manually Scheduled | Install flashing at parapet walls | 4 days | 2017 August 20 8:00 AM | 2017 August 23 5:00 PM | 82 | 2
88 | Yes | Auto Scheduled | Pour lightweight concrete roof fill | 2 days | 2020 August 20 8:00 AM | 2020 August 21 5:00 PM | 11,82,87 | 2
89 | Yes | Auto Scheduled | Install seamless roofing material | 5 days | 2020 August 31 8:00 AM | 2020 September 04 5:00 PM | 88FS+5d | 2
90 | Yes | Auto Scheduled | Spread stone ballast on seamless roof | 5 days | 2020 September 07 8:00 AM | 2020 September 11 5:00 PM | 89 | 2
91 | Yes | Auto Scheduled | Set rooftop equipment | 2 wks | 2020 September 14 8:00 AM | 2020 September 25 5:00 PM | 90 | 2
92 | Yes | Auto Scheduled | Window wall and store front closures | 60 days | 2020 August 18 8:00 AM | 2020 November 09 5:00 PM |  | 1
93 | Yes | Auto Scheduled | Install window wall aluminum and glass | 5 wks | 2020 August 18 8:00 AM | 2020 September 21 5:00 PM | 81 | 2
94 | Yes | Auto Scheduled | Install interior stud walls and drywall | 5 wks | 2020 September 22 8:00 AM | 2020 October 26 5:00 PM | 93 | 2
95 | Yes | Auto Scheduled | Install interior doors and hardware | 2 wks | 2020 October 27 8:00 AM | 2020 November 09 5:00 PM | 94 | 2
96 | Yes | Auto Scheduled | Install store front doors and hardware | 3 wks | 2020 August 18 8:00 AM | 2020 September 07 5:00 PM | 81 | 2
97 | Yes | Auto Scheduled | Finishing Building Works | 80 days | 2020 September 22 8:00 AM | 2021 January 11 5:00 PM |  | 1
98 | Yes | Auto Scheduled | Install millwork and wood trim | 3 wks | 2020 October 27 8:00 AM | 2020 November 16 5:00 PM | 96,94 | 2
99 | Yes | Auto Scheduled | Paint walls and woodwork | 4 wks | 2020 November 17 8:00 AM | 2020 December 14 5:00 PM | 98,95 | 2
100 | Yes | Auto Scheduled | Install conduit at ceiling plenum space | 3 wks | 2020 September 22 8:00 AM | 2020 October 12 5:00 PM | 93 | 2
101 | Yes | Auto Scheduled | Install duct in ceiling plenum space | 3 wks | 2020 October 27 8:00 AM | 2020 November 16 5:00 PM | 94,100 | 2
102 | Yes | Auto Scheduled | Install ceiling grid | 2 wks | 2020 November 17 8:00 AM | 2020 November 30 5:00 PM | 94,101 | 2
103 | Yes | Auto Scheduled | Install ceiling tile | 2 wks | 2020 December 01 8:00 AM | 2020 December 14 5:00 PM | 102 | 2
104 | Yes | Auto Scheduled | Hang wallpaper | 2 wks | 2020 December 01 8:00 AM | 2020 December 14 5:00 PM | 102 | 2
105 | Yes | Auto Scheduled | Install building carpet | 4 wks | 2020 December 15 8:00 AM | 2021 January 11 5:00 PM | 99 | 2
106 | Yes | Auto Scheduled | Install hardware and accessories | 3 wks | 2020 December 15 8:00 AM | 2021 January 04 5:00 PM | 99 | 2
107 | Yes | Auto Scheduled | Complete interior and exterior sod and plantings | 2 wks | 2020 December 15 8:00 AM | 2020 December 28 5:00 PM | 99 | 2
108 | Yes | Auto Scheduled | Pave, curb, and stripe parking lot | 2 wks | 2020 December 29 8:00 AM | 2021 January 11 5:00 PM | 107 | 2
109 | Yes | Auto Scheduled | Setting and Testing Elevators | 40 days | 2020 April 21 8:00 AM | 2020 June 15 5:00 PM |  | 1
110 | Yes | Auto Scheduled | Set elevator equipment in shafts | 4 wks | 2020 April 21 8:00 AM | 2020 May 18 5:00 PM | 80,45,12 | 2
111 | Yes | Auto Scheduled | Set equipment in mechanical room | 2 wks | 2020 May 19 8:00 AM | 2020 June 01 5:00 PM | 110 | 2
112 | Yes | Auto Scheduled | Test and align doors and equipment | 2 wks | 2020 June 02 8:00 AM | 2020 June 15 5:00 PM | 111 | 2
113 | Yes | Auto Scheduled | Plumbing | 90 days | 2020 August 25 8:00 AM | 2020 December 28 5:00 PM |  | 1
114 | Yes | Auto Scheduled | Rough-in plumbing in drywall walls | 4 wks | 2020 September 22 8:00 AM | 2020 October 19 5:00 PM | 93 | 2
115 | Yes | Auto Scheduled | Tie-in fire line riser and set valves | 2 wks | 2020 August 25 8:00 AM | 2020 September 07 5:00 PM | 84 | 2
116 | Yes | Auto Scheduled | Set plumbing fixtures and trim | 3 wks | 2020 October 20 8:00 AM | 2020 November 09 5:00 PM | 85,114,79 | 2
117 | Yes | Auto Scheduled | Flush, test, and clean piping and fixtures | 2 wks | 2020 December 15 8:00 AM | 2020 December 28 5:00 PM | 99,115,116 | 2
118 | Yes | Auto Scheduled | Electrical | 139 days | 2020 June 03 8:00 AM | 2020 December 14 5:00 PM |  | 1
119 | Yes | Auto Scheduled | Rough-in electrical in masonry walls | 4 wks | 2020 June 03 8:00 AM | 2020 June 30 5:00 PM | 75,14 | 2
120 | Yes | Auto Scheduled | Rough-in electrical in drywall walls | 4 wks | 2020 September 22 8:00 AM | 2020 October 19 5:00 PM | 93 | 2
121 | Yes | Auto Scheduled | Pull wire in conduit and set area transformers | 3 wks | 2020 October 13 8:00 AM | 2020 November 02 5:00 PM | 119,100 | 2
122 | Yes | Auto Scheduled | Install and terminate electrical devices | 3 wks | 2020 November 03 8:00 AM | 2020 November 23 5:00 PM | 121,120 | 2
123 | Yes | Auto Scheduled | Make electrical terminations for HVAC equipment | 2 days | 2020 November 03 8:00 AM | 2020 November 04 5:00 PM | 121,91 | 2
124 | Yes | Auto Scheduled | Install light fixtures - test and clean | 2 wks | 2020 December 01 8:00 AM | 2020 December 14 5:00 PM | 102,122 | 2
125 | Yes | Auto Scheduled | Heating and Ventilating - AC | 180 days | 2020 April 21 8:00 AM | 2020 December 28 5:00 PM |  | 1
126 | Yes | Auto Scheduled | Set equipment in mechanical room | 2 wks | 2020 April 21 8:00 AM | 2020 May 04 5:00 PM | 80,15 | 2
127 | Yes | Auto Scheduled | Rough-in mechanical in masonry walls | 4 wks | 2020 June 03 8:00 AM | 2020 June 30 5:00 PM | 75 | 2
128 | Yes | Auto Scheduled | Rough-in mechanical in drywall walls | 2 wks | 2020 September 22 8:00 AM | 2020 October 05 5:00 PM | 93 | 2
129 | Yes | Auto Scheduled | Install duct in building chase | 3 wks | 2020 September 22 8:00 AM | 2020 October 12 5:00 PM | 126,127,93 | 2
130 | Yes | Auto Scheduled | Set HVAC trim and test and balance system | 4 wks | 2020 December 01 8:00 AM | 2020 December 28 5:00 PM | 102,129,123 | 2
131 | Yes | Auto Scheduled | Final Clean-up and Occupancy | 60 days | 2020 October 27 8:00 AM | 2021 January 18 5:00 PM |  | 1
132 | Yes | Auto Scheduled | Install hard tile flooring in common areas | 1 wk | 2020 October 27 8:00 AM | 2020 November 02 5:00 PM | 94 | 2
133 | Yes | Auto Scheduled | Clean hard tile floors | 4 days | 2020 November 03 8:00 AM | 2020 November 06 5:00 PM | 132 | 2
134 | Yes | Auto Scheduled | Remove debris from building and do final clean-up | 4 days | 2021 January 12 8:00 AM | 2021 January 15 5:00 PM | 105,104,106,107,117,124,103,133 | 2
135 | Yes | Auto Scheduled | Substantial completion date | 1 day | 2021 January 18 8:00 AM | 2021 January 18 5:00 PM | 134 | 2
136 | Yes | Auto Scheduled | Complete Final Inspections | 6 days | 2021 January 18 8:00 AM | 2021 January 25 5:00 PM |  | 1
137 | Yes | Auto Scheduled | Complete elevator inspection and certification | 3 days | 2021 January 18 8:00 AM | 2021 January 20 5:00 PM | 134,112 | 2
138 | Yes | Auto Scheduled | Perform architect's inspection | 1 day | 2021 January 21 8:00 AM | 2021 January 21 5:00 PM | 134,108,137 | 2
139 | Yes | Auto Scheduled | Perform local building agency inspection | 1 day | 2021 January 22 8:00 AM | 2021 January 22 5:00 PM | 138 | 2
140 | Yes | Auto Scheduled | Perform Fire Marshal's inspection | 1 day | 2021 January 25 8:00 AM | 2021 January 25 5:00 PM | 139 | 2
141 | Yes | Auto Scheduled | Project Closure | 13 days | 2021 January 26 8:00 AM | 2021 February 11 5:00 PM |  | 1
142 | Yes | Auto Scheduled | Complete punch list items from all inspections | 2 wks | 2021 January 26 8:00 AM | 2021 February 08 5:00 PM | 140 | 2
143 | Yes | Auto Scheduled | Obtain certificate of occupancy | 2 days | 2021 February 09 8:00 AM | 2021 February 10 5:00 PM | 142 | 2
144 | Yes | Auto Scheduled | Issue final completion documents including warranties | 1 day | 2021 February 09 8:00 AM | 2021 February 09 5:00 PM | 142 | 2
145 | Yes | Auto Scheduled | Issue final request for payment | 1 day | 2021 February 11 8:00 AM | 2021 February 11 5:00 PM | 143,144 | 2

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
0 |  |  | Commercial Office Space Construction |  |  |  |  | 100% | $0.00/h | 0
1 | General Management | G | Work |  |  |  |  | 100% | $0.00/h | 0
2 | Project Management | P | Work |  |  |  |  | 100% | $0.00/h | 0
3 | Procurement | P | Work |  |  |  |  | 100% | $0.00/h | 0
4 | Scheduler | S | Work |  |  |  |  | 100% | $0.00/h | 0
5 | Accounting | A | Work |  |  |  |  | 100% | $0.00/h | 0
6 | Superintendent | S | Work |  |  |  |  | 100% | $0.00/h | 0
7 | Survey Crew | S | Work |  |  |  |  | 100% | $0.00/h | 0
8 | Rough Carpenter Crew | R | Work |  |  |  |  | 100% | $0.00/h | 0
9 | Labor Crew | L | Work |  |  |  |  | 100% | $0.00/h | 0
10 | Concrete Crew | C | Work |  |  |  |  | 100% | $0.00/h | 0
11 | Finish Carpenter Crew | F | Work |  |  |  |  | 100% | $0.00/h | 0
12 | Site Grading Contractor | S | Work |  |  |  |  | 100% | $0.00/h | 0
13 | Plumbing Contractor | P | Work |  |  |  |  | 100% | $0.00/h | 0
14 | Plumbing Contractor Management | P | Work |  |  |  |  | 100% | $0.00/h | 0
15 | Electric Contractor | E | Work |  |  |  |  | 100% | $0.00/h | 0
16 | Electric Contractor Management | E | Work |  |  |  |  | 100% | $0.00/h | 0
17 | HVAC Contractor | H | Work |  |  |  |  | 100% | $0.00/h | 0
18 | HVAC Contractor Management | H | Work |  |  |  |  | 100% | $0.00/h | 0
19 | Elevator Contractor | E | Work |  |  |  |  | 100% | $0.00/h | 0
20 | Elevator Contractor Management | E | Work |  |  |  |  | 100% | $0.00/h | 0
21 | Steel Erection Contractor | S | Work |  |  |  |  | 100% | $0.00/h | 0
22 | Steel Erection Contractor Management | S | Work |  |  |  |  | 100% | $0.00/h | 0
23 | Drywall Contractor | D | Work |  |  |  |  | 100% | $0.00/h | 0
24 | Masonry Contractor | M | Work |  |  |  |  | 100% | $0.00/h | 0
25 | Tile Contractor | T | Work |  |  |  |  | 100% | $0.00/h | 0
26 | Roofing Contractor | R | Work |  |  |  |  | 100% | $0.00/h | 0
27 | Roofing Contractor Management | R | Work |  |  |  |  | 100% | $0.00/h | 0
28 | Window Contractor | W | Work |  |  |  |  | 100% | $0.00/h | 0
29 | Carpet Contractor | C | Work |  |  |  |  | 100% | $0.00/h | 0
30 | Landscape Contractor | L | Work |  |  |  |  | 100% | $0.00/h | 0
31 | Paving Contractor | P | Excavation and Foundations |  |  |  |  | 100% | $0.00/h | 0
32 | Painting Contractor | P | Work |  |  |  |  | 100% | $0.00/h | 0
Column Erection and Miscellaneous steel works
Forming, Pouring, & Curing - Floors and Roof
Finishing Building Works
Setting and Testing Elevators

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Receive notice to proceed and sign contract | General Management | 0 | Commercial Office Space Construction | 100%
Submit bond and insurance documents | Project Management | 0 | 16h | 100%
Submit bond and insurance documents | General Management | 0 | 4h | 25%
Prepare and submit project schedule | Project Management | 0 | 4h | 25%
Prepare and submit project schedule | Scheduler | 0 | 16h | 100%
Prepare and submit schedule of values | General Management | 0 | 1.6h | 10%
Prepare and submit schedule of values | Project Management | 0 | 16h | 100%
Obtain building permits | Project Management | 0 | 16h | 50%
Obtain building permits | Procurement | 0 | 16h | 50%
Submit preliminary shop drawings | Project Management | 0 | 40h | 50%
Submit preliminary shop drawings | Procurement | 0 | 40h | 50%
Submit shop drawings and order long lead items - steel | Steel Erection Contractor Management | 0 | 80h | 100%
Submit shop drawings and order long lead items - roofing | Roofing Contractor Management | 0 | 80h | 100%
Submit shop drawings and order long lead items - elevator | Elevator Contractor Management | 0 | 80h | 100%
Submit shop drawings and order long lead items - plumbing | Plumbing Contractor Management | 0 | 80h | 100%
Submit shop drawings and order long lead items - electric | Electric Contractor Management | 0 | 80h | 100%
Submit shop drawings and order long lead items - HVAC | HVAC Contractor Management | 0 | 80h | 100%
Detail, fabricate and deliver steel | Steel Erection Contractor Management | 0 | 240h | 50%
Detail, fabricate and deliver steel | Steel Erection Contractor | 0 | 240h | 50%
Install temporary power | Electric Contractor | 0 | 16h | 100%
Install temporary water service | Plumbing Contractor | 0 | 16h | 100%
Set up site office | Superintendent | 0 | 24h | 100%
Set up site office | Labor Crew | 0 | 2.4h | 10%
Set line and grade benchmarks | Survey Crew | 0 | 24h | 100%
Prepare site - lay down yard and temporary fencing | Site Grading Contractor | 0 | 16h | 100%
Prepare site - lay down yard and temporary fencing | Labor Crew | 0 | 1.6h | 10%
Clear and grub site | Site Grading Contractor | 0 | 24h | 100%
Stone site access and temporary parking area | Site Grading Contractor | 0 | 16h | 100%
Rough grade site (cut and fill) | Site Grading Contractor | 0 | 40h | 100%
Install storm drainage | Site Grading Contractor | 0 | 80h | 100%
Install exterior fire line and building fire riser | Plumbing Contractor | 0 | 80h | 100%
Perform final site grading | Site Grading Contractor | 0 | Excavation and Foundations | 100%
Erect building batter boards and layout building | Survey Crew | 0 | 40h | 100%
Excavate foundations | Site Grading Contractor | 0 | 40h | 50%
Excavate elevator pit | Site Grading Contractor | 0 | 16h | 100%
Form column piers and spread foundations | Rough Carpenter Crew | 0 | 32h | 100%
Rough-in electric and plumbing in elevator | Plumbing Contractor | 0 | 32h | 100%
Rough-in electric and plumbing in elevator | Electric Contractor | 0 | 32h | 100%
Form elevator pit walls | Rough Carpenter Crew | 0 | 32h | 100%
Set reinforcing and anchor bolts | Rough Carpenter Crew | 0 | 32h | 100%
Pour column piers and foundations | Concrete Crew | 0 | 40h | 100%
Pour concrete elevator walls | Concrete Crew | 0 | 8h | 100%
Cure elevator wall concrete | Labor Crew | 0 | 5.6h | 10%
Cure piers and foundations | Labor Crew | 0 | 5.6h | 10%
Strip wall forms | Labor Crew | 0 | 0.8h | 10%
Strip column piers and foundation forms | Labor Crew | 0 | 24h | 100%
Install pneumatic tube in elevator pit | Elevator Contractor | 0 | Column Erection and Miscellaneous steel works | 100%
Prepare and pour concrete floor in elevator pit | Concrete Crew | 0 | 8h | 100%
Erect steel columns, beams and joint - 1st and 2nd floors | Steel Erection Contractor | 0 | 80h | 100%
Erect steel columns, beams and joint - 3rd floor and roof | Steel Erection Contractor | 0 | 80h | 100%
Install miscellaneous iron and bracing - 1st and 2nd floors | Steel Erection Contractor | 0 | 60h | 75%
Install miscellaneous iron and bracing - 3rd floor and roof | Steel Erection Contractor | 0 | 60h | 75%
Install stairs and miscellaneous iron railing | Steel Erection Contractor | 0 | 40h | 50%
Touch-up paint on steel | Steel Erection Contractor | 0 | Forming, Pouring, & Curing - Floors and Roof | 20%
Form 2nd floor including all floor openings | Rough Carpenter Crew | 0 | 40h | 100%
Form 2nd floor including all floor openings | Labor Crew | 0 | 8h | 20%
Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Labor Crew | 0 | 13.2h | 33%
Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Plumbing Contractor | 0 | 13.2h | 33%
Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Electric Contractor | 0 | 13.2h | 33%
Pour 2nd floor slab | Concrete Crew | 0 | 32h | 100%
Cure 2nd floor slab | Labor Crew | 0 | 5.6h | 10%
Strip forms from 2nd floor slab | Labor Crew | 0 | 16h | 100%
Form 3rd floor including all floor openings | Rough Carpenter Crew | 0 | 20h | 50%
Form 3rd floor including all floor openings | Labor Crew | 0 | 8h | 20%
Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Labor Crew | 0 | 13.2h | 33%
Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Plumbing Contractor | 0 | 13.2h | 33%
Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Electric Contractor | 0 | 13.2h | 33%
Pour 3rd floor slab | Concrete Crew | 0 | 32h | 100%
Cure 3rd floor slab | Labor Crew | 0 | 5.6h | 10%
Strip forms from 3rd floor slab | Labor Crew | 0 | 16h | 100%
Form roof slab including all floor openings | Rough Carpenter Crew | 0 | 40h | 100%
Form roof slab including all floor openings | Labor Crew | 0 | 8h | 20%
Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Labor Crew | 0 | 13.2h | 33%
Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Plumbing Contractor | 0 | 13.2h | 33%
Install rebar and in-floor utilities (including mechanical, electrical, plumbing) | Electric Contractor | 0 | 13.2h | 33%
Pour roof slab | Concrete Crew | 0 | 32h | 100%
Cure roof slab | Labor Crew | 0 | 5.6h | 10%
Strip forms from roof slab | Labor Crew | 0 | 16h | 100%
Form 1st floor | Rough Carpenter Crew | 0 | 32h | 100%
Install electrical underground | Electric Contractor | 0 | 40h | 100%
Install plumbing underground | Plumbing Contractor | 0 | 40h | 100%
Install rebar and in-floor utilities | Labor Crew | 0 | 10.57h | 33%
Install rebar and in-floor utilities | Plumbing Contractor | 0 | 10.57h | 33%
Install rebar and in-floor utilities | Electric Contractor | 0 | 10.57h | 33%
Pour 1st floor slab | Concrete Crew | 0 | 32h | 100%
Cure 1st floor slab | Labor Crew | 0 | 5.6h | 10%
Strip forms from 1st floor slab | Labor Crew | 0 | 16h | 100%
Install exterior sheathing and metal studs | Drywall Contractor | 0 | 120h | 100%
Rough-in plumbing at toilets and masonry walls | Plumbing Contractor | 0 | 160h | 100%
Lay masonry at core, mechanical, and toilets | Masonry Contractor | 0 | 160h | 100%
Install exterior masonry work | Masonry Contractor | 0 | 200h | 100%
Install roof drains | Roofing Contractor | 0 | 16h | 100%
Install tile in toilet rooms | Tile Contractor | 0 | 80h | 100%
Clean masonry | Masonry Contractor | 0 | 20h | 50%
Clean toilet room tile | Tile Contractor | 0 | 20h | 50%
Install flashing at parapet walls | Roofing Contractor | 0 | 32h | 100%
Pour lightweight concrete roof fill | Roofing Contractor | 0 | 16h | 100%
Install seamless roofing material | Roofing Contractor | 0 | Finishing Building Works | 100%
Spread stone ballast on seamless roof | Roofing Contractor | 0 | 40h | 100%
Set rooftop equipment | HVAC Contractor | 0 | 80h | 100%
Install window wall aluminum and glass | Window Contractor | 0 | 200h | 100%
Install interior stud walls and drywall | Drywall Contractor | 0 | 200h | 100%
Install interior doors and hardware | Finish Carpenter Crew | 0 | 80h | 100%
Install store front doors and hardware | Window Contractor | 0 | 120h | 100%
Install millwork and wood trim | Finish Carpenter Crew | 0 | 120h | 100%
Paint walls and woodwork | Painting Contractor | 0 | 160h | 100%
Install conduit at ceiling plenum space | Electric Contractor | 0 | 120h | 100%
Install duct in ceiling plenum space | HVAC Contractor | 0 | 120h | 100%
Install ceiling grid | Drywall Contractor | 0 | 80h | 100%
Install ceiling tile | Drywall Contractor | 0 | Setting and Testing Elevators | 100%
Hang wallpaper | Painting Contractor | 0 | 80h | 100%
Install building carpet | Carpet Contractor | 0 | 160h | 100%
Install hardware and accessories | Finish Carpenter Crew | 0 | 120h | 100%
Complete interior and exterior sod and plantings | Landscape Contractor | 0 | 80h | 100%
Pave, curb, and stripe parking lot | Paving Contractor | 0 | 80h | 100%
Set elevator equipment in shafts | Elevator Contractor | 0 | 160h | 100%
Set equipment in mechanical room | Elevator Contractor | 0 | 80h | 100%
Test and align doors and equipment | Elevator Contractor | 0 | 80h | 100%
Rough-in plumbing in drywall walls | Plumbing Contractor | 0 | 160h | 100%
Tie-in fire line riser and set valves | Plumbing Contractor | 0 | 80h | 100%
Set plumbing fixtures and trim | Plumbing Contractor | 0 | 120h | 100%
Flush, test, and clean piping and fixtures | Plumbing Contractor | 0 | 80h | 100%
Rough-in electrical in masonry walls | Electric Contractor | 0 | 160h | 100%
Rough-in electrical in drywall walls | Electric Contractor | 0 | 160h | 100%
Pull wire in conduit and set area transformers | Electric Contractor | 0 | 120h | 100%
Install and terminate electrical devices | Electric Contractor | 0 | 120h | 100%
Make electrical terminations for HVAC equipment | Electric Contractor | 0 | 16h | 100%
Install light fixtures - test and clean | Electric Contractor | 0 | 80h | 100%
Set equipment in mechanical room | HVAC Contractor | 0 | 80h | 100%
Rough-in mechanical in masonry walls | HVAC Contractor | 0 | 160h | 100%
Rough-in mechanical in drywall walls | HVAC Contractor | 0 | 80h | 100%
Install duct in building chase | HVAC Contractor | 0 | 120h | 100%
Set HVAC trim and test and balance system | HVAC Contractor | 0 | 160h | 100%
Install hard tile flooring in common areas | Tile Contractor | 0 | 40h | 100%
Clean hard tile floors | Tile Contractor | 0 | 16h | 50%
Remove debris from building and do final clean-up | Labor Crew | 0 | 32h | 100%
Substantial completion date | Superintendent | 0 | 8h | 100%
Complete elevator inspection and certification | Elevator Contractor | 0 | 24h | 100%
Perform architect's inspection | Superintendent | 0 | 4h | 50%
Perform architect's inspection | Project Management | 0 | 4h | 50%
Perform local building agency inspection | Project Management | 0 | 4h | 50%
Perform local building agency inspection | Superintendent | 0 | 4h | 50%
Perform Fire Marshal's inspection | Superintendent | 0 | 4h | 50%
Perform Fire Marshal's inspection | Project Management | 0 | 4h | 50%
Complete punch list items from all inspections | Superintendent | 0 | 8.8h | 11%
Complete punch list items from all inspections | Labor Crew | 0 | 8.8h | 11%
Complete punch list items from all inspections | Plumbing Contractor | 0 | 8.8h | 11%
Complete punch list items from all inspections | Electric Contractor | 0 | 8.8h | 11%
Complete punch list items from all inspections | HVAC Contractor | 0 | 8.8h | 11%
Complete punch list items from all inspections | Drywall Contractor | 0 | 8.8h | 11%
Complete punch list items from all inspections | Carpet Contractor | 0 | 8.8h | 11%
Complete punch list items from all inspections | Paving Contractor | 0 | 8.8h | 11%
Complete punch list items from all inspections | Painting Contractor | 0 | 8.8h | 11%
Obtain certificate of occupancy | Project Management | 0 | 16h | 100%
Issue final completion documents including warranties | Project Management | 0 | 8h | 100%
Issue final request for payment | Project Management | 0 | 2.63h | 33%
Issue final request for payment | Accounting | 0 | 2.63h | 33%
Issue final request for payment | General Management | 0 | 2.63h | 33%